## Slide 1: Nuclear Technology

## Slide 2
UK NUCLEAR PROGRAMME LANDSCAPE
Programme Overview at a Glance
Construction / active delivery
Design & consenting
Site selection
CONSTRUCTION
Hinkley Point C
3.2 GW · 2×EPR
MILESTONE First power 2030
EDF Energy · CGN
CONSTRUCTION
Sizewell C
3.2 GW · 2×EPR
MILESTONE FID July 2025 · build to 2033–37
EDF · UK Gov (44.9%) · La Caisse · Centrica
PRE-FID DESIGN
Rolls-Royce SMR — Wylfa
1.4 GW+ · 3×470 MWe (up to 8 units)
MILESTONE Grid connection mid-2030s · FID ~2029
GBE-N · Rolls-Royce SMR
SITE SELECTION
Further Large-Scale Site
~3.2 GW equivalent
MILESTONE GBE-N site report Autumn 2026
GBE-N · DESNZ
PRE-CONSTRUCTION
STEP Fusion — West Burton
~100 MWe prototype
MILESTONE DCO by March 2029 · demo ~2040
UK Fusion Energy · UKAEA
ACTIVE DELIVERY
Sellafield Decommissioning
UK's largest nuclear clean-up site
MILESTONE Full site remediation by 2125
Sellafield Ltd · NDA · PPP
Source: UK Nuclear Programme Landscape Report — Market & Supply Chain Analysis, 22 June 2026. Figures subject to revision at future approval gateways.

## Slide 3
UK NUCLEAR & FUSION PROGRAMME LANDSCAPE
Delivery Timeline, 2026–2040+
Construction / active delivery
Design & consenting
Site selection
2026
2028
2030
2032
2034
2036
2038
2040
2042+
Hinkley Point C
3.2 GW · EDF Energy · CGN
First power
Sizewell C
3.2 GW · EDF · UK Gov · La Caisse · Centrica
FID Jul-25 (signed)
Construction complete (range)
Rolls-Royce SMR — Wylfa
1.4 GW+ · GBE-N · Rolls-Royce SMR
FID (target)
Grid connection (mid-2030s)
Further Large-Scale Site
~3.2 GW equivalent · GBE-N · DESNZ
GBE-N site report, Autumn 2026
STEP Fusion — West Burton
~100 MWe prototype · UK Fusion Energy · UKAEA
DCO submission, Mar-29
Net-energy demo (~2040)
NDA
Decommissioning
UK's largest clean-up site · Sellafield Ltd · NDA · PPP
Full remediation by 2125 →
TODAY
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​

## Slide 4
UK PRIVATE SMR / AMR / MMR PROJECTS
Programme Overview at a Glance
Construction / contracted delivery
GDA / site-specific licensing
MOU / feasibility
GDA STEP 2 COMPLETE
Holtec SMR-300 — Cottam
2×320 MWe+ · ~$11bn
MILESTONE GDA Step 2 done Mar-26 · operational 2030s
Holtec · EDF Energy · Tritax
PRE-GDA / LICENSING
Westinghouse AP300 — Seal Sands
4×300 MWe · 1.5 GW total
MILESTONE Site fully licensed (target 2027) · ops early 2030s
Westinghouse · Community Nuclear Power
GDA SUBMITTED
X-energy Xe-100 — Hartlepool
12×80 MWe (960 MWe) · ~£40bn lifetime value
MILESTONE GDA submitted Jun-26 · concludes end-2029
X-energy · Centrica
MOU / FEASIBILITY
Last Energy PWR-20 — London Gateway
20 MWe micro-reactor · £80m private investment
MILESTONE Operations targeted 2030
Last Energy · DP World
Source: public company/government announcements as of 22 June 2026. None of these projects has reached FID; figures are developer-stated targets and subject to material change as GDA, site licensing and financing progress.

## Slide 5
UK PRIVATE SMR / AMR / MMR PROJECTS
Emerging Programme Timeline, 2025–2034+
Construction / contracted delivery
GDA / site-specific licensing
MOU / feasibility
2025
2026
2027
2028
2029
2030
2031
2032
2033
2034+
Holtec SMR-300 — Cottam
2 × 320 MWe (+) · Holtec · EDF · Tritax · ~$11bn
MOU signed, Sep-25
GDA Step 2 complete, Mar-26
Operational (2030s)
Westinghouse AP300 — Seal Sands
4 × 300 MWe (1.5 GW) · Westinghouse · Community Nuclear Power
Design certification · site fully licensed (target)
Construction begins
Operation (early 2030s)
X-energy Xe-100 — Hartlepool
12 × 80 MWe (960 MWe) · X-energy · Centrica · £40bn lifetime
JDA signed, Sep-25
GDA submitted, Jun-26
GDA concludes (end 2029)
Last Energy PWR-20 — London Gateway
20 MWe micro-reactor · Last Energy · DP World · £80m private investment
MOU signed, Sep-25
Operations targeted, 2030
TODAY
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​
First power, mid-2030s

## Slide 6
BWRX-300: 2026 Programme Update
UK nuclear sector briefing for manufacturing supply chain partners
GDA Step 2
Completed 21 Jan 2026 —
fastest UK GDA to date
14 units
SGE fleet proposal:
4.2GW across 3 UK sites
£35bn
SGE investment target;
first power sought by 2034
1st in G7
BWRX-300 under construction
at Darlington, Canada
2025–26 STATUS TIMELINE
Apr '25
GEH submits final tender to Great British Nuclear alongside Rolls-Royce and Holtec; Rolls-Royce is selected as preferred bidder for Wylfa two months later.
21 Jan '26
BWRX-300 completes UK GDA Step 2 — 'no fundamental shortfalls' found; the fastest two-step GDA engagement completed to date.
4 Feb '26
Government publishes the new Advanced Nuclear Framework (ANF) — a private-sector route to market for advanced/SMR projects, separate from the GBE-N competition GEH lost.
1 Jul '26
SGE (a European SMR developer) submits an ANF application to build 14 BWRX-300 units (4.2GW) across three UK sites, backed by a consortium including Samsung C&T, Laing O'Rourke, Aecon, Google Cloud and Fermi Development; £35bn investment, first power targeted 2034.
WHAT IT MEANS FOR YOU
The 'no UK pathway' story has just changed: SGE's 14-unit, 4.2GW proposal is a concrete, privately financed UK route for the BWRX-300 — filed under the new Advanced Nuclear Framework rather than the GBE-N competition GEH lost.
The GDA Step 2 pass is genuinely strong evidence of design maturity — fastest ever completed — so this fleet proposal starts from a lower-risk technology base than most competitors.
Google Cloud and Fermi Development's involvement signals this fleet is being driven by data centre/AI power demand — a different commercial logic worth flagging to SMEs eyeing that sector.
This is a proposal, not a confirmed project: ANF applications go through phased government assessment before any endorsement or support is confirmed — worth tracking progress rather than treating it as done.
Ongoing '26
BWRX-300 momentum continues globally (Darlington construction, Poland, Sweden, Southeast Asia MoUs); UK supply chain MoUs with Sheffield Forgemasters, Aecon, AtkinsRéalis, Jacobs, Amentum and Laing O'Rourke remain in place.
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​
Notes: Key talking points: GE Vernova Hitachi (GEH) was one of four finalists in the Great British Nuclear SMR competition (alongside Rolls-Royce, Holtec and Westinghouse), submitting its final tender on 11 April 2025. Rolls-Royce was selected as preferred bidder in June 2025, so GEH - like Westinghouse - did not win the government-backed Wylfa contract. Regulatory progress has been strong throughout: the BWRX-300 opted for ONR's newer, shorter two-step GDA process and completed Step 2 on 21 January 2026 - the fastest two-step GDA engagement completed to date, with regulators finding no fundamental safety, security, safeguards or environmental shortfalls. BIG UPDATE (July 2026): the UK pathway question has been answered. On 4 February 2026 the government published the new Advanced Nuclear Framework (ANF), a first-of-its-kind route for privately led advanced/SMR projects to seek government assessment, in-principle endorsement and potential support (revenue mechanisms, National Wealth Fund investment) - entirely separate from the GBE-N competition GEH lost. Applications opened on a continuous basis from 4 March 2026. On 1 July 2026, SGE - a European SMR development and investment platform, previously known for Polish SMR ambitions - announced it had submitted an ANF application to build FOURTEEN GE Vernova Hitachi BWRX-300 units (4.2GW combined) across THREE UK sites. This would supply an estimated 11% of UK power demand, equivalent to almost 8 million homes, for at least 60 years. SGE has set up a dedicated UK project vehicle, SGE SMR UK Limited. Total investment is put at GBP35bn, with first electricity targeted by 2034. The SGE deployment consortium is broad and notable: alongside SGE and GE Vernova Hitachi Nuclear Energy, it includes Samsung C&T, Laing O'Rourke, Aecon Group, Google Cloud, Fermi Development, Etara and an unnamed experienced nuclear operator. The presence of Google Cloud and Fermi Development strongly suggests this fleet is aimed at least partly at powering AI/data centre demand, similar in spirit to Holtec-EDF's Cottam proposal covered elsewhere in this briefing series. Caveat to flag to the room: this is a submitted proposal, not a confirmed, funded project. ANF applications go through a phased process (Rapid Project Triage, then a Project Deep Dive across five core areas: technology/supply chain, developer capability, finance, siting, and operator/end-use arrangements) before receiving any government endorsement - there is no guarantee of the timeline or outcome. GEH's existing UK supply chain relationships remain relevant background: an MoU with Sheffield Forgemasters (nuclear-grade forgings) since 2022, plus MoUs with AtkinsRealis, Jacobs, Amentum, Boccard and Cavendish Nuclear (Laing O'Rourke and Aecon now also appear directly in the SGE consortium). Globally, BWRX-300 remains under construction at Ontario Power Generation's Darlington site in Canada (first SMR in the G7), with further momentum in Poland, Sweden and Southeast Asia. Framing for the room: this is a significant status change from earlier in this briefing series - GEH has gone from 'strong technology, no clear UK route' to having a large, well-capitalised private consortium actively pursuing UK deployment via the brand-new Advanced Nuclear Framework, just one day before this update was prepared.

## Slide 7
SMR-300: 2026 Programme Update
UK nuclear sector briefing for F4N cohort July 2026
Step 2
UK GDA passed –
no fundamental shortfalls
4 units
Proposed at Cottam,
Nottinghamshire (~1.3GW)
£1.5bn
South Yorkshire
SMR-300 factory
70%
UK content target
for factory build
2026 MILESTONE TIMELINE
13 Feb
US NRC officially accepts Holtec's Pioneer 1 & 2 Construction Permit Application for review (Palisades, Michigan). Safety/environmental review due early-mid 2027.
31 Mar
SMR-300 completes Step 2 of the UK Generic Design Assessment (GDA). No fundamental shortfalls across 21 technical areas; 14 regulatory observations to resolve.
23 Jun
Holtec and EDF Energy sign Heads of Terms for a joint venture and jointly submit a proposal for up to four SMR-300 units at the former Cottam coal site, Nottinghamshire.
24 Jun
Cottam proposal confirmed publicly: ~1.3GW capacity, targeting power for co-located data centres; Holtec signals plans for a larger UK operations centre and is evaluating a UK manufacturing plant.
WHAT IT MEANS FOR YOU
A second live UK SMR pipeline alongside Wylfa: South Yorkshire (factory) plus now Cottam (deployment site). More entry points beyond Rolls-Royce.
70% UK-content ambition for the South Yorkshire factory mirrors Rolls-Royce's target. Early positioning now could pay off across both programmes.
GDA Step 2 success is a strong safety-case signal, but Step 3 (site-specific) hasn't started. Cottam design work is the next real procurement trigger.
Holtec is explicitly evaluating a UK manufacturing plant on top of South Yorkshire. A further, currently-open opportunity to watch.
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​
Notes: Key talking points: Holtec's SMR-300 completed Step 2 of the UK GDA on 31 March 2026 - regulators (ONR, EA, NRW) found no fundamental shortfalls across 21 technical topic areas, though 14 regulatory observations remain to be resolved. Holtec has not yet asked regulators to proceed to Step 3 (site-specific) of the GDA. 23-24 June: Holtec and EDF Energy signed Heads of Terms for a joint venture and submitted a joint proposal to government for up to four SMR-300 units (~1.3GW) at the former Cottam coal site in Nottinghamshire, intended partly to power co-located data centres. Holtec said it plans to substantially expand its UK operations centre and is evaluating a separate UK manufacturing plant. Background (pre-2026, useful context if asked): Holtec selected South Yorkshire in Sept 2024 as the site for a proposed GBP1.5bn SMR-300 factory, targeting at least 70% UK content in materials, components and work; MoUs were signed with the AMRC (Sheffield) and MTC (Coventry) to support manufacturing and testing development. On the US side: 13 Feb 2026, the US NRC accepted Holtec's Construction Permit Application for the twin Pioneer 1 & 2 SMR-300 units at Palisades, Michigan, for review, with safety/environmental evaluations expected complete by early-to-mid 2027 - this is the first-of-a-kind project that Cottam would follow as second-of-a-kind.

## Slide 8
PWR-20: 2026 Programme Update
UK nuclear sector briefing for F4N cohort July 2026
PDR passed
First UK developer to
complete Preliminary Design Review
£80m
DP World London
Gateway microreactor
$100m+
Series C funding,
closed Dec 2025
SIP filed
Llynfi planning notice,
11 June 2026
2025–26 STATUS TIMELINE
Jun '25
PWR-20 completes the UK's first-ever Preliminary Design Review; ONR says a December 2027 site licence decision remains achievable if Last Energy delivers to schedule.
Sep '25
MoU signed with DP World for an £80m, subsidy-free micro-nuclear plant at London Gateway (Thames Freeport, Essex). Targeting operation in 2030. Support the port's £1 billion terminal expansion and its all-electric berths.
Dec '25
Closes an oversubscribed third major round of investment of $100m+, led by Astera Institute, strengthening the balance sheet behind its UK projects.
11 Jun '26
Last Energy UK notifies Welsh Government of intent to submit a Significant Infrastructure Project application for the 4-unit Llynfi (Bridgend) project; formal application expected July 2026. Selling to local industrial customers, including mid-size manufacturers and various commercial businesses in the region.
WHAT IT MEANS FOR YOU
A fundamentally different model: no government competition to win. Last Energy builds, owns and operates plants, selling power directly to industrial customers on-site, entirely privately financed.
At 20MWe, PWR-20 uses roughly 40 truck-transportable modules. Far smaller, simpler components than the 300-470MWe reactors from Rolls-Royce, Holtec or Westinghouse, and a more accessible entry point for smaller manufacturers.
Two live UK sites now in play (Llynfi, Wales and London Gateway, Essex) plus international deals. A growing pipeline, but no Last Energy reactor has been built anywhere yet.
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​
Notes: Key talking points: Last Energy is a US micro-nuclear developer (spin-off of the Energy Impact Center) pursuing a build-own-operate model with its PWR-20, a 20 MWe / 80 MWt pressurised water reactor sold directly to industrial customers rather than into the grid via a government competition.
Its flagship UK project is the Llynfi Clean Energy Project (Prosiect Egni Glan Llynfi) - four PWR-20 units at the former Llynfi coal power station site in Bridgend County, South Wales, first announced Oct 2024, GBP300m capital investment, no public funding. In Feb 2025 it became the first new site for a commercial nuclear reactor to enter ONR site licensing since Torness in 1978. In June 2025 the PWR-20 completed the UK's first-ever Preliminary Design Review; ONR stated a Dec 2027 site licence decision remains achievable IF Last Energy delivers submissions to schedule and standard - note the conditional phrasing, this is not a guarantee. In September 2025, alongside President Trump's UK state visit, Last Energy signed an MoU with DP World for an GBP80m, subsidy-free PWR-20 microreactor at London Gateway port (Thames Freeport, Essex), targeting operation in 2030 - a second live UK site distinct from Llynfi. In December 2025 Last Energy closed an oversubscribed Series C of over $100m led by the Astera Institute. The clearest confirmed 2026 UK-specific milestone: on 11 June 2026, Last Energy UK filed a notification of intent with the Welsh Government to submit a Significant Infrastructure Project (SIP) application under the Infrastructure (Wales) Act 2024 for the Llynfi project, with the formal SIP application expected in July 2026 - essentially happening right around now. Planning documents released alongside this show a site layout with four reactors. Caveats worth flagging to the room: industry insiders (quoted anonymously by New Civil Engineer) have called the 2027 delivery target 'over-ambitious', and Last Energy has never built, owned or operated an operating nuclear power plant anywhere in the world - its Texas A&M PWR-5 pilot is a smaller demonstration unit still in the safety-review stage with the US DOE. Present this as a genuine but higher-risk, earlier-stage opportunity relative to Rolls-Royce, Holtec, X-energy and Westinghouse.

## Slide 9
LFR-AS-200: UK Programme Update
UK nuclear sector briefing for F4N cohort July 2026
Suspended
UK reactor programme
paused, July 2025
London→Paris
HQ relocated,
October 2024
€645m
Total funds raised
since 2021
~150
UK staff retained
despite pause
2024–26 STATUS TIMELINE
Oct '24
Newcleo relocates its holding headquarters from London to Paris, citing focus on its European precursor and prototype reactor programme.
Jun '25
LFR-AS-200 becomes the first Advanced Modular Reactor design accepted into the UK's Generic Design Assessment. A genuine first for the sector, achieved without public funding.
Jul '25
Newcleo announces it is suspending its UK reactor development programme and substantially winding down UK activities, citing lack of access to the UK's plutonium stockpile and insufficient government backing for Gen IV technology.
Feb '26
Closes a further €75m funding round (€105m raised in 12 months); continues to prioritise Italy, France and Slovakia over the UK for near-term deployment.
WHAT IT MEANS FOR YOU
A genuine cautionary tale: even a vendor that hit a real UK regulatory first (first AMR into GDA, no public funding needed) pulled back when policy support didn't follow. A useful reminder that GDA entry alone isn't a supply chain signal.
The core issue was fuel policy, not technology: government's 2025 decision to immobilise the UK's plutonium stockpile rather than release it for reactor fuel removed Newcleo's core UK value proposition.
Newcleo says it could 'ramp up' again if the AMR policy outlook improves. So worth a watching brief rather than active engagement for now.
If you have Gen IV / lead-cooled fast reactor capability, France, Italy and Slovakia are currently the live opportunities with Newcleo, not the UK.
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​
Notes: Key talking points: Newcleo is a France-headquartered (originally UK-founded, in 2021) developer of the LFR-AS-200, a 200 MWe lead-cooled fast reactor (Gen IV), designed to run on MOX fuel from reprocessed spent fuel/plutonium. In June 2025 it became the first Advanced Modular Reactor design ever accepted into the UK's Generic Design Assessment process - a genuine regulatory first, and achieved without any public funding, which the company was keen to highlight. Despite this, in July 2025 Newcleo announced it was suspending its UK reactor development programme and substantially winding down UK activities. The stated reason was twofold: (1) the UK government's 2025 decision to immobilise its ~140-tonne civil plutonium stockpile at Sellafield rather than make it available for reactor fuel, which undercut Newcleo's core recycled-fuel value proposition, and (2) a broader view that alternative UK routes to market for Gen IV/AMR technology (via GBE-N and the National Wealth Fund) were unlikely to offer timely, tangible support compared to opportunities elsewhere. Newcleo has retained a reduced UK team of around 150 staff to maintain a UK presence and allow it to scale back up if the policy outlook improves - this is explicitly a pause, not a full exit, but there is no confirmed timeline for reactivation. The company continues to be very active elsewhere in Europe: joint venture with Slovakia's JAVYS for up to four LFRs, an agreement with the Lithuanian government, and continued fundraising (closed a further EUR75m round in Feb 2026, taking 12-month total to over EUR105m and lifetime total to around EUR645m). Its PRECURSOR non-nuclear test reactor in Italy is targeted for completion by end of 2026. Framing for the room: this is the most important cautionary example in the whole briefing series. It shows that GDA entry and technical credibility are not sufficient on their own - UK government fuel and industrial policy decisions can cause a well-funded, technically serious vendor to deprioritise the UK even after a genuine regulatory first. Worth flagging as a risk factor for any SME considering committing significant capacity to a single UK SMR/AMR vendor relationship.

## Slide 10
: 2026 Programme Update
UK nuclear sector briefing for F4N cohort July 2026
3
European markets
with signed contracts
£599m
UK National Wealth
Fund investment
£12m
Pioneer Works, Derby
manufacturing centre
~8,000
UK jobs supported
per year (est.)
2026 MILESTONE TIMELINE
Feb
Yokogawa Electric appointed to supply control systems (Runcorn design facility).
13 Apr
Contract signed with Great British Energy – Nuclear (GBE-N) for site-specific design at Wylfa; long lead-time equipment ordering begins.
24 Apr
Early Works Contract signed with CEZ Group for Czech Republic's first SMR at Temelín (up to 3GW).
May
Škoda JS and Doosan Enerbility appointed as dual suppliers for nuclear island components. Sparked UK industry debate on the 70% UK-content ambition.
15 Jun
Selected by Videberg Kraft (Vattenfall) to deliver 3 SMRs at Värö Peninsula, Sweden — third European contract win.
26 Jun
Pioneer Works manufacturing development centre announced for Derby — precision assembly, welding & testing, ~40 skilled roles.
WHAT IT MEANS FOR YOU
Only supplier with multiple signed SMR contracts in Europe (UK, Czechia, Sweden), Programme momentum is real, not speculative.
Overseas nuclear-island awards (Škoda JS, Doosan) show the 70% UK-content target is contested. A live opportunity to press the case for UK-based capability.
Pioneer Works, Derby opens a near-term route in for precision assembly, welding and testing suppliers.
GBE-N contract unlocks ordering of long lead-time equipment. Early engagement window for tier 2/3 suppliers is now.
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​
Notes: Key talking points: RR SMR is now the only company with multiple contractual SMR commitments in Europe (UK, Czechia, Sweden). GDA (Generic Design Assessment) has been running since April 2022 and is expected to complete in 2026 - flag if asked, this is the regulatory gateway. The Skoda JS / Doosan Enerbility nuclear island component award in May drew criticism from UK politicians/industry over the 70% UK-content commitment - good discussion point with SMEs about where the real opportunity and pressure points are. Pioneer Works in Derby (announced 26 June) is a near-term, tangible entry point for SME engagement - manufacturing development centre, ~40 roles, non-nuclear site. Half year RR Group results due 30 July 2026 may add further detail.

## Slide 11
AP300: 2026 Programme Update
UK nuclear sector briefing for F4N cohort July 2026
Withdrew
From GBN/Wylfa competition,
April 2025
4 units
Private AP300 fleet planned,
North Teesside
80 yrs
Springfields fuel site
milestone, March 2026
Step 1
UK GDA complete;
Step 2 assessment ongoing
2025–26 STATUS TIMELINE
Apr '25
Westinghouse withdraws from Great British Nuclear's government-backed SMR competition; Rolls-Royce is selected as the UK's preferred partner two months later.
2025
Six UK supplier MoUs signed (William Cook, Trillium Flow, Curtiss-Wright UK, Boccard UK, Bendalls Engineering, Sheffield Forgemasters) to support AP1000/AP300 component supply.
30 Mar '26
Springfields, Lancashire marks 80 years as the world's oldest continuously operating nuclear fuel manufacturing site — the anchor of Westinghouse's UK footprint.
Ongoing '26
AP300 remains in the UK's 2-step GDA (Step 1 complete). Community Nuclear Power continues developing the privately financed 4-unit AP300 fleet at North Teesside, targeting a licensed site by 2027.
WHAT IT MEANS FOR YOU
Unlike Rolls-Royce, Holtec and X-energy, Westinghouse is not part of the government-backed Wylfa programme. Its UK SMR future rests entirely on the privately financed Teesside project, a different risk profile to weigh.
AP300 reuses AP1000 engineering and components, so its supplier base is already established. A lower-risk, faster route in for suppliers with existing PWR experience.
Watch CNP's 2027 licensed-site target for Teesside closely. That milestone, not the GDA, is the clearest near-term signal of whether this programme moves from ambition to funded construction.
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​
Notes: Key talking points: Westinghouse's UK SMR story in 2026 is quieter than Rolls-Royce, Holtec or X-energy because it withdrew from the government-backed Great British Nuclear (GBN, now GBE-N) competition in April 2025 without submitting a final tender - Rolls-Royce was announced as the preferred bidder for the Wylfa programme in June 2025. This means Westinghouse's near-term UK reactor ambitions now rest on the privately financed Community Nuclear Power (CNP) project - four AP300 units at North Teesside, first announced Feb 2024, targeting a fully licensed site by 2027 and commercial operation in the early 2030s. No major public update on CNP/Teesside progress was found dated specifically to 2026 - worth checking closer to the presentation date, and flagging this data gap if asked directly. The AP300 remains in the UK's two-step GDA process; Step 1 (scope agreement) was completed in 2024/2025, and Step 2 (detailed technical assessment) is understood to be ongoing, though no specific 2026 completion milestone was confirmed in available sources - avoid stating Step 2 is complete. The clearest confirmed 2026 UK news is the 30 March 2026 milestone marking 80 years of continuous operation at the Springfields fuel fabrication site in Lancashire - a good story about long-term UK nuclear manufacturing heritage, and a reminder that Westinghouse's UK footprint doesn't depend solely on AP300 succeeding. In 2025, Westinghouse signed MoUs with six UK suppliers (William Cook Cast Products, Trillium Flow Technology, Curtiss-Wright Controls UK, Boccard UK, Bendalls Engineering, Sheffield Forgemasters) covering valves, pumps, pressure vessels and forged steel components for AP1000/AP300 - useful named contacts for SMEs asking how to get involved. Framing for the room: this is a useful contrast slide - Westinghouse shows what happens when a well-established, technically de-risked design (AP300 reuses AP1000 engineering) doesn't win the main government competition, and has to find another route to market.

## Slide 12
Xe-100: 2026 Programme Update
UK nuclear sector briefing for F4N cohort July 2026
6 GW
Proposed UK fleet
at Hartlepool
GDA
Xe-100 submitted
June 2026
$1bn+
Raised in Nasdaq IPO,
April 2026
£40bn
Estimated lifetime
UK economic value
2026 MILESTONE TIMELINE
Feb
US NRC approves the TX-1 fuel facility's Part 70 licence for TRISO-X fuel handling — first Category II licence ever issued, underpinning future UK fuel supply.
Apr
UK Government confirms Future Nuclear Enabling Fund award (£6.68m total programme); Kier Group joins as UK constructability and supply chain partner.
24 Apr
X-energy lists on Nasdaq (ticker: XE), raising over $1bn. The largest nuclear IPO on record, strengthening capacity to fund global deployment including the UK.
2 Jun
Xe-100 HTGR formally submitted into the UK Generic Design Assessment (GDA). Regulatory review expected to conclude by end of 2029.
16 Jun
Closes $700m Series D: $1.4bn raised in a year, $1.8bn total; 144 SMR orders logged globally (11GW), including the Centrica UK partnership.
WHAT IT MEANS FOR YOU
Earliest-stage UK programme of the three: GDA only just submitted, not expected to conclude until end-2029. Longer runway to prepare, but least near-term certainty.
Xe-100 is a helium-cooled, graphite-moderated HTGR, not a PWR like Rolls-Royce or Holtec. Different specialisms in play: graphite components, high-temperature materials, helium systems.
Kier Group is already engaged on UK constructability and supply chain analysis. A live route in for tier 1/2 UK contractors and manufacturers.
No UK manufacturing site announced yet (unlike Rolls-Royce's Derby or Holtec's South Yorkshire). But the post-IPO balance sheet signals a serious, well-funded long-term entrant.
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​
Notes: Key talking points: X-energy's Xe-100 is a pebble-bed high-temperature gas-cooled reactor (HTGR) using TRISO-X fuel - materially different technology from the pressurised water reactor designs offered by Rolls-Royce and Holtec, so it draws on a different supplier base (graphite, helium handling, high-temp alloys). UK plan is centred on Hartlepool, developed with Centrica and EDF, targeting up to 6GW / 12 units in the fleet's first phase (JDA signed Sept 2025 - background, not 2026, but useful context). 2 June 2026: Xe-100 formally submitted for UK GDA; the regulator (ONR/EA/NRW/DESNZ) expects the assessment to conclude by end of 2029 - much later than Holtec's GDA Step 2 completion, so this is the least regulatorily mature of the three programmes covered in this series. 24 April 2026: X-energy IPO'd on Nasdaq under ticker XE, raising over $1bn - the largest nuclear IPO on record - shortly followed by a $700m Series D in June, taking total raised to roughly $1.8bn. This financial strength is worth flagging to SMEs as a signal of staying power. Kier Group's involvement (announced as part of the Future Nuclear Enabling Fund-backed work) is the clearest current UK contractor/supply-chain touchpoint - worth suggesting SMEs track Kier's subcontracting activity here. No UK factory or manufacturing site has been announced for X-energy, unlike Rolls-Royce (Derby) and Holtec (South Yorkshire) - flag this contrast if useful.

## Slide 13
: 2026 Programme Update
UK nuclear sector briefing for manufacturing supply chain partners
£1.3bn
Government funding for
STEP via UK Fusion Energy
£200m
ILIOS Construction Partner
initial contract
£70m
Tokamak Energy magnets
contract to March 2029
8,000
Peak construction jobs
expected at West Burton
2026 MILESTONE TIMELINE
14 Jan–11 Mar
First public consultation on STEP Fusion's Development Consent Order held across North Nottinghamshire, Lincolnshire and South Yorkshire communities.
Mar
ILIOS consortium (Kier-Nuvia joint venture, with AECOM, AL_A and Turner & Townsend) appointed Construction Partner — £200m initial 3-4.5 year contract, up to 8,000 jobs at peak.
23 Mar
UKAEA completes first phase of West Burton site acquisition from EDF — land transferred 3.5 years ahead of schedule; demolition and ash extraction under way.
14 Apr
Tokamak Energy named Magnet Systems Partner — £70m contract to March 2029, delivered via TE Magnetics, securing UK sovereign HTS magnet capability.
Mid-Apr
At Fusion Fest 2026, UK Fusion Energy and UKAEA launch strategies to 2030/2040 alongside the Government's national Fusion Strategy; £30m Dassault Systèmes digital/PLM deal signed.
WHAT IT MEANS FOR YOU
STEP is a single UK national programme, not a multi-vendor competition — the entry point is UKFE's own procurement portal, not a company sales team.
Already a live, spending programme: £108.8m industry spend to date (£91.8m in the UK), 813 suppliers, 49 already local to West Burton — this is not just a future promise.
ILIOS (Construction Partner) is the near-term route in for civil, construction and engineering SMEs; Tokamak Energy's magnet contract shows a second wave of specialist technology subcontracting now opening up.
Longer horizon than any SMR programme (operations targeted 2040) but de-risked fast in 2026: site owned, construction partner and magnets partner both under contract, and £2.5bn government funding committed to FY2029/30.
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​
Notes: Key talking points: STEP (Spherical Tokamak for Energy Production) is the UK's prototype fusion power plant programme, led by UK Fusion Energy Ltd (UKFE, formerly UK Industrial Fusion Solutions/UKIFS), a wholly owned subsidiary of the UK Atomic Energy Authority (UKAEA). It is being built at the former West Burton A coal-fired power station in Nottinghamshire, targeting net electricity generation (~100MWe) and tritium self-sufficiency, with operations expected to begin around 2040. 2026 has been a landmark year of moving 'from concept into delivery'. Key confirmed milestones: the first public (non-statutory) consultation on the Development Consent Order ran 14 January to 11 March 2026 across communities in North Nottinghamshire, Lincolnshire and South Yorkshire. In March 2026, the ILIOS consortium - a Kier/Nuvia (VINCI Construction) joint venture with AECOM, AL_A architects and Turner & Townsend - was appointed as STEP's Construction Partner, under an initial GBP200m contract covering roughly 3-4.5 years, with the programme expected to support up to 8,000 jobs at peak construction and potentially grow to GBP10bn in future phases. On 23 March 2026, UKAEA completed the first phase of acquiring the West Burton site from EDF, with land transferred three and a half years ahead of schedule - EDF continues transitional operations on parts of the site while demolition and ash extraction continue elsewhere. On 14 April 2026, Tokamak Energy was named STEP's Magnet Systems Partner under a GBP70m contract running to March 2029, delivering eight magnet-related work packages via its TE Magnetics division - a significant UK sovereign capability win, since Tokamak Energy is the UK's only specialist manufacturer of high-field HTS magnet technology. In mid-April 2026, at Fusion Fest 2026 in London, UK Fusion Energy and UKAEA jointly launched their strategies (to 2040 and 2030 respectively) alongside the Government's own national Fusion Strategy, confirming GBP2.5bn of fusion investment across FY2025/26-2029/30, of which GBP1.3bn is allocated directly to STEP. A GBP30m digital/PLM agreement with Dassault Systemes (3DEXPERIENCE platform) was also signed at this event. Framing for the room: unlike every other programme in this briefing series, STEP is not a vendor competing for UK business - it IS the UK's own programme, run by a public body, with its own dedicated supply chain portal. As of Jan 2026 the programme reports 813 total suppliers, 49 of them local to the West Burton/Trent Valley area (part of the emerging 'Trent Clean Energy Supercluster' alongside neighbouring former coal sites Cottam and High Marnham), and GBP108.8m of industry spend to date, GBP91.8m of which stayed within the UK. This is a genuinely different, and arguably lower-risk, category of opportunity for SMEs: a government-backed programme with committed multi-year funding, rather than a private vendor betting on winning a competition or attracting investment.

## Slide 14
Decommissioning Programmes: 2026 Update
UK nuclear sector briefing for manufacturing supply chain partners
£1.8bn
NDA group's annual
supply chain spend
£45m
SME win: LTi Metaltech,
Sellafield SRP, Feb 2026
New
Strategy
NDA group Strategy
effective March 2026
1st AGRs
Hunterston B & Hinkley Pt B
transfer to NDA in 2026
2026 MILESTONE TIMELINE
Oct '25
Three companies win contracts worth up to £2.9bn for non-nuclear infrastructure works at Sellafield — context for the scale of work entering the market into 2026.
18 Feb
Sellafield awards a £45m contract to LTi Metaltech — a UK fabrication and welding SME — to supply plutonium storage containers ('100-year cans') for the new Product and Residue Store Retreatment Plant.
23 Feb
NDA publishes its latest group Strategy, effective March 2026 — a refreshed long-term roadmap prioritising hazard reduction, integration and collaboration across the NDA estate.
During '26
Hunterston B becomes the first Advanced Gas-cooled Reactor site to transfer from EDF Energy to the NDA group for decommissioning, with Hinkley Point B to follow — NDA's first significant new mission since creation.
21 May
Sellafield's Programme and Project Partners (PPP) marks 7 years, with major projects (SRP, SIXEP Continuity Plant, BEPPS2, LSS1) progressing through construction and design.
WHAT IT MEANS FOR YOU
This is the largest, steadiest source of UK nuclear manufacturing demand in this whole briefing series — £1.8bn spent every year, for decades, regardless of how any single SMR programme fares.
LTi Metaltech's £45m win is a genuine template: a UK fabrication/welding SME became a brand-new Sellafield supplier through open competitive tender, and is now investing locally — proof the door is open to newcomers, not just incumbents.
The mission is expanding, not winding down: AGR sites transferring in during 2026 open new decades-long site programmes layered on top of existing Sellafield and Magnox work.
Structured entry points exist: the annual NDA Supply Chain Event (Europe's largest), the cross-estate Shared Services Alliance procurement pipeline, and Sellafield's own new supplier process are all live routes in.
Commercial in Confidence - This document contains proprietary and commercially sensitive information. It is intended solely for the recipient(s) and should not be disclosed or distributed without written permission from Nuclear Collaboration Ltd (NucCol ltd) Co. no. 15937779 ​
Notes: Key talking points: the Nuclear Decommissioning Authority (NDA) is a very different category of opportunity to everything else in this briefing series - it is not building new reactors, it is safely decommissioning the UK's 17 legacy nuclear sites (dating back to the 1940s), managing spent fuel and nuclear materials, and developing a Geological Disposal Facility (GDF) for the UK's most hazardous waste. Its mission is expected to run into the next century. The NDA group comprises Sellafield Ltd, Nuclear Restoration Services (NRS, the former Magnox sites), Nuclear Waste Services (NWS, leading the GDF programme), and various other subsidiaries. Combined annual supply chain spend across the group is around GBP1.8 billion - by far the largest and steadiest number in this whole SMR/AMR briefing series, and one that isn't contingent on any single reactor programme succeeding. The clearest, most SME-relevant story of 2026 so far: on 18 February, Sellafield awarded a GBP45m contract to LTi Metaltech, a UK fabrication and welding SME, to supply 'containment products' (nuclear-grade storage containers known as '100-year cans') for the Sellafield Product and Residue Store Retreatment Plant (SRP), which will repackage the UK's plutonium stockpile for long-term storage. This is a genuinely good story to tell SMEs: LTi Metaltech was a brand-new addition to Sellafield's supply chain, won via open competitive tender using Sellafield's new 'product introduction process', and is now investing in a welding school, local SME partnerships and a Cumbrian logistics facility. Worth noting SRP construction began in Feb 2020, is due for active commissioning in 2027 and will operate until around 2060 - illustrating the decades-long nature of this work. On 23 February 2026, NDA published its latest group Strategy (effective from March 2026), a refreshed long-term roadmap organised around three strategic themes: spent nuclear fuels, nuclear materials (plutonium and uranium), and integrated waste management, with a stronger emphasis on integration and collaboration across the NDA group. A genuinely new mission is starting in 2026: Hunterston B is on track to be the first Advanced Gas-cooled Reactor (AGR) site to transfer from EDF Energy to the NDA group (via Nuclear Restoration Services) for decommissioning, with Hinkley Point B to follow - described by NDA's own business plan as its 'first significant new mission' since its creation in 2005, with the rest of the seven-strong AGR fleet to transfer over subsequent years, funded via the Nuclear Liabilities Fund. Arrangements are also progressing (subject to government approval) to transfer the Ministry of Defence's Vulcan site, adjacent to Dounreay, to the NDA. On 21 May 2026, Sellafield's Programme and Project Partners (PPP) - a delivery alliance of KBR, Amentum, Morgan Sindall Infrastructure and Altrad Babcock plus wider supply chain - marked seven years, with major projects progressing: the SIXEP Continuity Plant, Box Encapsulation Plant Product Store 2 (BEPPS2) now in early construction, and Lightly Shielded Store 1 (LSS1) finalising design. Other 2026 context worth mentioning if asked: NRS is starting work to reduce the height of two reactor buildings at Trawsfynydd in North Wales, described as a first-of-its-kind opportunity for Wales; Nuclear Waste Services continues community engagement with two Cumbria communities on potential GDF siting; and government has asked NDA and Cumberland Council to explore clean energy development (including new nuclear) on NDA-owned land at Moorside, adjacent to Sellafield. Framing for the room: decommissioning is the 'unsexy' but most reliable and immediate opportunity in UK civil nuclear for manufacturing SMEs - it doesn't require winning a national competition or waiting for a reactor design to be licensed, and the annual NDA Supply Chain Event (held every November, recognised as the largest supply chain event of its kind in Europe) is a direct, practical way in.

## Slide 15
UK SUBMARINE DEFENCE PROGRAMMES
Programme Overview at a Glance
In service / active build
Detailed design / long-lead procurement
Concept / pre-contract
ACTIVE BUILD / FINISHING
Astute Class (SSN)
7 boats · ~£12bn+ programme
MILESTONE
5 in service · Achilles (final boat) enters service 2029
Drumbeat winding down as Barrow workforce transitions to Dreadnought/AUKUS
BAE Systems · Submarine Delivery Agency
ACTIVE BUILD
Dreadnought Class (SSBN)
4 boats · ~£41bn
MILESTONE
All 4 boats cut · first in service early 2030s · CASD to 2060s
Continuous-at-sea deterrent replacement; UK's single largest defence programme
BAE Systems · Rolls-Royce · Submarine Delivery Agency
DESIGN / LONG-LEAD
SSN-AUKUS (SSN)
Up to 12 boats (UK) · ~£2.5bn/boat
MILESTONE
D2L2 design phase · first UK boat delivered late 2030s
Barrow infrastructure investment cited as a programme risk by Defence Committee
BAE Systems · Rolls-Royce · Babcock

## Slide 16
UK SUBMARINE DEFENCE PROGRAMMES
Build & Delivery Timeline, 2026–2045+
In service / active build
Detailed design / long-lead procurement
Concept / pre-contract
2026
2029
2032
2035
2038
2041
2045+
Astute Class (SSN)
7 boats · ~£12bn+ programme · BAE Systems · Submarine Delivery Agency
5 boats in service · Agamemnon in trials
HMS Achilles (boat 7, final) enters service
Dreadnought Class (SSBN)
4 boats · ~£41bn · BAE Systems · Rolls-Royce · Submarine Delivery Agency
All 4 boats cut/in build · KGV steel cut Sep-25
HMS Dreadnought enters service (early 2030s)
Class complete, replaces Vanguard (CASD to 2060s)
SSN-AUKUS (SSN)
Up to 12 boats (UK) · ~£2.5bn/boat · BAE Systems · Rolls-Royce · Babcock
D2L2 design phase · 4 PWR3+ reactors in build
Long-lead procurement concludes
First UK boat delivered (late 2030s)
TODAY

## Slide 17
UK Nuclear Submarine Fleet: 2026 Update
UK nuclear sector briefing for manufacturing supply chain partners
Up to 12
SSN-AUKUS attack
submarines confirmed
21,000
UK jobs supported
at peak production
£9bn+
Rolls-Royce reactor
agreement, Derby
4 reactors
PWR3+ units under
construction, May 2026
2025–26 MILESTONE TIMELINE
26 Jul '25
UK and Australia sign the Geelong Treaty — a 50-year bilateral agreement governing joint construction of Australia's SSN-AUKUS submarines.
22 Feb '26
HMS Anson becomes the first Royal Navy nuclear submarine to undergo a maintenance period in Australia, at HMAS Stirling; five Australian firms supply components for the visit.
24 Feb '26
Australia announces a A$310m payment to the UK for long-lead reactor items; manufacture of complete welded nuclear propulsion systems begins at Rolls-Royce Submarines, Derby.
10 Apr '26
Australian Submarine Supplier Qualification programme expanded to link Australian businesses into UK submarine supply chains for the first time — a reciprocal industrial pathway.
28 Apr '26
UK Parliament's Defence Committee warns of 'shortcomings and failings', flagging delays to the Barrow shipyard upgrade and submarine availability as 'critically low'.
May '26
Defence Secretary John Healey confirms four PWR3+ reactors are under construction at the expanded Rolls-Royce Raynesway facility in Derby.
WHAT IT MEANS FOR YOU
This is the largest sustained nuclear manufacturing programme in this whole briefing series — up to 12 boats, one every 18 months, 21,000 jobs at peak, with billions already committed to Barrow and Derby.
There's no vendor competition here: Rolls-Royce Submarines (reactors, Derby) and BAE Systems (hulls/assembly, Barrow) are fixed primes — the opportunity for SMEs is as tier 2/3 suppliers into their established chains, including Cardiff and Glasgow.
Genuine delivery risk is on the record: Parliament's own Defence Committee flagged shipyard investment delays and 'critically low' submarine availability — a reminder to weigh real execution risk against the funding headlines.
The trilateral structure is opening two-way industrial access, with Australian firms now qualifying into UK supply chains and vice versa — a sign the ecosystem is becoming genuinely international.
Notes: Key talking points: this slide covers the UK's nuclear-powered submarine enterprise, which sits alongside (and is much larger than) the civil SMR/AMR programmes covered elsewhere in this briefing series. It spans three current/future submarine classes: the Astute-class SSN (last boat due into service around 2026), the Dreadnought-class SSBN (strategic deterrent, in build into the 2030s), and the new SSN-AUKUS (SSN-A), the next-generation attack submarine being developed jointly with Australia and the US under AUKUS Pillar 1. In the UK's Strategic Defence Review (June 2025), government confirmed it will acquire a fleet of up to 12 SSN-AUKUS submarines, replacing the Astute class from the late 2030s, with continuous production targeting a new submarine roughly every 18 months. At peak, the programme is projected to sustain around 21,000 UK jobs, with the wider Defence Nuclear Enterprise projected to support around 65,000 UK jobs by 2030. Over £6bn has been invested in critical infrastructure at Barrow-in-Furness (BAE Systems, hull construction and final assembly) and Raynesway, Derby (Rolls-Royce Submarines, reactor manufacture) since mid-2024, with more than 3,000 new jobs already created across key UK nuclear sites. SSN-AUKUS will be powered by the Rolls-Royce PWR3+ pressurised water reactor, an enhanced version of the PWR3 used in the Dreadnought class; reactor cores are designed to last the full operational life of the boat. In May 2026, Defence Secretary John Healey confirmed four PWR3+ reactors were under construction at Raynesway. Industrial contracts already placed include roughly £4bn for design activities and a further approximately £9bn Rolls-Royce reactor agreement. The AUKUS partnership with Australia has moved from agreement to delivery through 2025-26: the 50-year Geelong Treaty was signed 26 July 2025; in February 2026 HMS Anson became the first Royal Navy nuclear submarine to undergo maintenance in Australia (at HMAS Stirling, Western Australia), with five Australian companies manufacturing components for the visit; and later that month Australia announced a A$310m payment to the UK to secure long-lead reactor items, with manufacture beginning at Rolls-Royce Derby for Australia's first two SSN-AUKUS boats (the UK supplies complete, welded nuclear propulsion systems since Australia, as a non-nuclear-weapon state, does not produce its own submarine nuclear fuel). In April 2026, Australia's Submarine Supplier Qualification programme (AUSSQ) was expanded to link Australian businesses into UK submarine supply chains for the first time - a genuinely reciprocal, trilateral industrial base is forming. Important balance for the room: in April 2026, the UK Parliament's Defence Committee published a report warning of 'shortcomings and failings' threatening the programme, specifically flagging delays to the planned shipyard upgrade investment at Barrow and describing Royal Navy submarine availability as 'critically low' (partly due to Astute-class boats being stretched by AUKUS-related port visits and rotations). This is a useful, credible counterweight to the otherwise very positive government messaging, and worth citing to give the room a balanced picture. Framing for the room: unlike every civil SMR/AMR vendor covered in this series, there is no competition to win here - Rolls-Royce Submarines and BAE Systems are the fixed prime contractors for reactors and hulls respectively. For manufacturing SMEs, the realistic route in is as a tier 2/3 subcontractor into their established supply chains, concentrated around Derby, Barrow-in-Furness, Cardiff and Glasgow - and, increasingly, with export potential into the parallel Australian and US legs of the AUKUS programme.

## Slide 18: Country

## Slide 19: Country

## Slide 20
SOUTH AFRICA NUCLEAR PROGRAMME LANDSCAPE
Programme Overview at a Glance
Operational / active delivery
Policy mandate / pre-procurement / R&D
Concept / early stage
OPERATIONAL (RELICENSED)
Koeberg Units 1 & 2
1,860 MWe combined · ~5% of SA electricity
MILESTONE Licensed to 2044 (U1) and 2045 (U2) · U2 record 365-day run, Mar-26
Eskom · NNR · Framatome
PRE-PROCUREMENT
New Build — Duynefontein/Thyspunt
5,200 MWe by 2039 · 1,200 MWe by 2036
MILESTONE Sites approved · reset RFP expected 2025/26 · no vendor selected
Eskom · DEE · NERSA · NNR
R&D / PRE-RFP
SMR / PBMR Revival
Scale not yet specified · Pelindaba (possible site)
MILESTONE Necsa preparing SMR-specific RFP
Necsa · Pelchem
CONCEPT / EARLY DEVELOPMENT
BridgePower Nuclear (private)
Thermal phase now · “Pearl SMR” modules from 2029
MILESTONE Thermal phase deployable in 12–24 months
USP&E · BAM Energy

## Slide 21
SOUTH AFRICA NUCLEAR PROGRAMME LANDSCAPE
Delivery Timeline, 2026–2040+
Operational / active delivery
Policy mandate / pre-procurement / R&D
Concept / early stage
2026
2028
2030
2032
2034
2036
2038
2040+
Koeberg Units 1 & 2
1,860 MWe combined · Eskom · NNR · Framatome
Both units relicensed (LTO complete)
Licensed to 2044 (U1) / 2045 (U2)
New Build — Duynefontein/Thyspunt/Bantamsklip
5,200 MWe by 2039 · Eskom · DEE · NERSA · NNR
Reset RFP expected 2025/26
First 1,200 MWe targeted online
SMR / PBMR Revival
Necsa · Pelchem · possible Pelindaba site
SMR-specific RFP in preparation
BridgePower Nuclear (private)
USP&E · BAM Energy
Thermal phase deployable (12–24mo)
“Pearl SMR” modules from 2029 (subject to FID)
TODAY
Source: Eskom, NNR, NERSA, Department of Electricity and Energy, World Nuclear Association announcements, 23 June 2026. Procurement timelines have a multi-year history of restart and delay; dates reflect policy intent absent a signed EPC contract.

## Slide 22
NETHERLANDS NUCLEAR PROGRAMME LANDSCAPE
Programme Overview at a Glance
Operational / active delivery
Siting / design / pre-FID
Concept / forward option
OPERATIONAL / LTO SOUGHT
Borssele — Long-Term Operation
482 MWe · ~3% of NL electricity
MILESTONE Due to close 2033 · extension to 2054 sought
EPZ · ANVS
SITING / FEASIBILITY
First Two New Reactors
2 × 1,000–1,650 MWe
MILESTONE Preferred site decision mid-2026 · operational “late 2030s” (slipped from 2035)
NEO NL · EDF · Westinghouse · KHNP · NEXUS-NL
CONCEPT / FORWARD OPTION
Third & Fourth Reactors
Scale and technology not yet announced
MILESTONE Announced March 2024 · targeted by 2050 · no site yet
Ministry of Climate and Green Growth
SITING / EARLY DEVELOPMENT
SMR Programme
13+ SMR potential by 2050 (150 MWe class)
MILESTONE Gelderland to designate 2 SMR sites in 2027
Rolls-Royce SMR · ULC-Energy · BAM Infra · Thorizon
Source: World Nuclear Association, World Nuclear News, Dutch government (Ministry of Climate and Green Growth), ANVS, NRG-Pallas announcements, 23 June 2026. Dates are policy targets and have already slipped once.

## Slide 23
NETHERLANDS NUCLEAR PROGRAMME LANDSCAPE
Delivery Timeline, 2026–2050+
Operational / active delivery
Siting / design / pre-FID
Concept / forward option
2026
2030
2034
2038
2042
2046
2050+
Borssele — Long-Term Operation
482 MWe · EPZ · ANVS · due to close 2033, extension to 2054 sought
Nuclear Energy Act amendment in parliament
Original closure date · extension to 2054 sought
First Two New Reactors
2×1,000–1,650 MWe · NEO NL · EDF/Westinghouse/KHNP studies · NEXUS-NL
Preferred site decision (mid-2026)
Operational “late 2030s” (slipped from 2035)
Third & Fourth Reactors
Site and technology not yet announced · Ministry of Climate and Green Growth
Announced March 2024, no site yet
Targeted by 2050
SMR Programme
Rolls-Royce SMR · ULC-Energy · BAM Infra · Gelderland siting · Thorizon MSR
Gelderland designates 2 SMR sites
Room for 13+ SMRs by 2050 (study)
TODAY
Source: World Nuclear Association, World Nuclear News, Dutch government (Ministry of Climate and Green Growth), ANVS, NRG-Pallas announcements, 23 June 2026. Dates are policy targets and have already slipped once; bar lengths illustrative.

## Slide 24
SWEDEN NUCLEAR PROGRAMME LANDSCAPE
Programme Overview at a Glance
Operational / contracted delivery
Permitting / planning / pre-FID
Concept / early stage
OPERATIONAL / LTO STUDIES
Existing Fleet — Forsmark & Ringhals
6 reactors · ~30% of Swedish electricity
MILESTONE 60→80-year life extension studies underway at both plants
Vattenfall · Uniper · Fortum · SSM
SUPPLIER SELECTED
Videberg Kraft — Ringhals/Värö SMR
3 × 470 MWe · ~1.5 GW · ~12 TWh/yr
MILESTONE Rolls-Royce SMR selected 15 Jun-26 · first reactor targeted early 2030s
Vattenfall · Industrikraft · Rolls-Royce SMR
EARLY PLANNING
Wider Municipal SMR Pipeline
Studsvik · Kärnfull Next · Blykalla (Gävle)
MILESTONE 13 feasibility studies done · new permitting law in force Jun–Jul 2026
Studsvik · Kärnfull Next · Blykalla
POLICY FRAMEWORK LIVE
National 2045 Ambition
2 large reactors by 2035 · 10-reactor equivalent by 2045
MILESTONE SEK 400bn credit guarantee + two-way CfD scheme now in force
Swedish Government · SSM
Source: Vattenfall, World Nuclear Association, World Nuclear News, Swedish Government, NucNet announcements, 23 June 2026. Rolls-Royce SMR was selected for Ringhals/Värö on 15 June 2026; FID for the project has not yet been taken.

## Slide 25
SWEDEN NUCLEAR PROGRAMME LANDSCAPE
Delivery Timeline, 2026–2045+
Operational / contracted delivery
Permitting / planning / pre-FID
Concept / early stage
2026
2029
2032
2035
2038
2041
2045+
Existing Fleet — Forsmark & Ringhals LTO
6 reactors, ~30% of SE electricity · Vattenfall · Uniper · Fortum · SSM
60→80-year life extension studies underway
Reactors remain in long-term use to 2040s
Videberg Kraft — Ringhals/Värö SMR
3 × 470 MWe (~1.5 GW) · Vattenfall · Industrikraft · Rolls-Royce SMR
Rolls-Royce SMR selected, 15 Jun-26
First reactor targeted early 2030s
Wider Municipal SMR Pipeline
Studsvik · Kärnfull Next · Blykalla (Gävle) · 13 municipal feasibility studies
New permitting law in force, Jun–Jul 2026
Multiple applications in early planning
National 2045 Ambition
2 large reactors by 2035 · equivalent of 10 new reactors by 2045 · Swedish Government
SEK 400bn credit guarantee framework live
“10 reactor equivalent” ambition (incl. SMRs)
TODAY
Source: Vattenfall, World Nuclear Association, World Nuclear News, Swedish Government, NucNet announcements, 23 June 2026. Rolls-Royce SMR was selected for Ringhals/Värö on 15 June 2026; FID for the project has not yet been taken.

## Slide 26
POLAND NUCLEAR PROGRAMME LANDSCAPE
Programme Overview at a Glance
Construction / active delivery
Licensing / design / pre-FID
Site selection / concept
LICENSING / PRE-CONSTRUCTION
Lubiatowo-Kopalino — Large Reactors
3 × Westinghouse AP1000 · 3,750 MWe · ~€42bn
MILESTONE
Construction licence application submitted Apr-26 · first concrete late 2028 · units online 2036–2038
EPC contract still under negotiation; site prep and geotechnical surveys underway since 2025
PEJ · Westinghouse · Bechtel
GENERIC DESIGN / SITING
OSGE — BWRX-300 SMR Fleet
Up to 24 × 300 MWe · Włocławek (first site)
MILESTONE
Poland Generic Design Agreement signed Feb-26 · first unit targeted 2032
Europe's first confirmed BWRX-300 deployment; fleet ambition across 3+ sites by early 2030s
Orlen · Synthos Green Energy · GE Vernova Hitachi
ENABLING FRAMEWORK LIVE
State Financing & EU Approval
Two-way CfD (40-year) · 100% state debt guarantee
MILESTONE
European Commission approved state aid Dec-25 · EXIM Bank credit agreement signed Feb-26
One of the largest state aid approvals in EU history; underpins bankability of the large-reactor programme
European Commission · EXIM Bank · Polish Ministry of Finance
Source: PEJ, Westinghouse, Bechtel, GE Vernova, OSGE, World Nuclear News, Polish Ministry of Energy announcements, 23 June 2026. EPC contract for the large-reactor programme is still under negotiation.

## Slide 27
POLAND NUCLEAR PROGRAMME LANDSCAPE
Delivery Timeline, 2026–2038+
Construction / active delivery
Licensing / design / pre-FID
Site selection / concept
2026
2028
2030
2032
2034
2036
2038+
Lubiatowo-Kopalino — Large Reactors
3 × Westinghouse AP1000 (3,750 MWe) · PEJ · Westinghouse · Bechtel · ~€42bn
Construction licence application submitted, Apr-26
First concrete (late 2028)
Unit 1 online 2036 · Units 2 & 3 by 2038
OSGE — BWRX-300 SMR Fleet
Up to 24 × 300 MWe · Orlen · Synthos Green Energy · GE Vernova Hitachi
Poland Generic Design Agreement signed, Feb-26
First unit (Włocławek) targeted 2032
Fleet build-out across 3+ sites continues
State Financing & EU Approval
Two-way CfD (40yr) · 100% debt guarantee · EXIM Bank · European Commission
EC approves state aid package, Dec-25
EXIM credit agreement signed, Feb-26
TODAY
Source: PEJ, Westinghouse, Bechtel, GE Vernova, OSGE, World Nuclear News, Polish Ministry of Energy announcements, 23 June 2026. EPC contract for the large-reactor programme is still under negotiation; bar lengths illustrative.

## Slide 28
CZECHIA NUCLEAR PROGRAMME LANDSCAPE
Programme Overview at a Glance
Operational / contracted construction
Licensing / engineering / early works
Option / pre-decision
OPERATIONAL / LTO UNDERWAY
Dukovany 1–4 — Long-Term Operation
4 × VVER-440 · ~30% of Czech electricity
MILESTONE 20-year extension programme underway, targeting 60-year operating life
ČEZ · SUŽEP
EPC SIGNED / EARLY WORKS
Dukovany 5 & 6 — KHNP APR-1000
2 × 1,050 MWe · CZK 407bn (~€16.5bn)
MILESTONE EPC signed Jun-25 · groundbreaking 2029 · units online 2036/2037
KHNP · EDU II · ČEZ · Doosan Enerbility
OPTION / PRE-DECISION
Temelín 3 & 4
Site identified · technology not yet selected
MILESTONE KHNP holds option to extend contract — decision window open to ~2028
ČEZ · Government of Czechia
EARLY WORKS CONTRACT
Rolls-Royce SMR — Temelín
Up to 3 GW · 470 MWe units
MILESTONE Early Works Contract signed 24 Apr-26 · approvals targeted by 2030
ČEZ (20% RR-SMR equity) · Rolls-Royce SMR
Source: ČEZ, KHNP, Rolls-Royce SMR, World Nuclear Association, World Nuclear News, NucNet announcements, 23 June 2026. Rolls-Royce SMR's Early Works Contract is not a Final Investment Decision.

## Slide 29
CZECHIA NUCLEAR PROGRAMME LANDSCAPE
Delivery Timeline, 2026–2038+
Operational / contracted construction
Licensing / engineering / early works
Option / pre-decision
2026
2028
2030
2032
2034
2036
2038+
Dukovany 1–4 — Long-Term Operation
4 × VVER-440 · ~30% of CZ electricity · ČEZ · SUŽEP
20-year extension programme underway (to 60yr life)
Last unit retires 2047 (beyond chart)
Dukovany 5 & 6 — KHNP APR-1000
2 × 1,050 MWe · CZK 407bn (~€16.5bn) · KHNP · EDU II · ČEZ
EPC signed Jun-25 · design/licensing docs filed Apr-26
Groundbreaking targeted 2029
Units online 2036 (U5) and 2037 (U6)
Temelín 3 & 4 — Option
KHNP eligible to extend contract within 3 years of Jun-25 EPC signing
Decision window open to ~2028
Rolls-Royce SMR — Temelín
Up to 3 GW (470 MWe units) · ČEZ (20% RR-SMR equity) · Rolls-Royce SMR
Early Works Contract signed, 24 Apr-26
Approvals targeted by 2030
First unit, second half of 2030s
TODAY
Source: ČEZ, KHNP, Rolls-Royce SMR, World Nuclear Association, World Nuclear News, NucNet announcements, 23 June 2026. Rolls-Royce SMR's Early Works Contract is not a Final Investment Decision; bar lengths illustrative.

## Slide 30
ROMANIA NUCLEAR PROGRAMME LANDSCAPE
Programme Overview at a Glance
Operational / contracted construction
Licensing / engineering / pre-FID
Option / forward planning
CIVIL WORKS UNDERWAY
Cernavodă Unit 1 — Refurbishment
650 MWe CANDU-6 · ~€1.9bn
MILESTONE Civil works begun Sep-25 · refurb outage Dec-26–Dec-28 · +30yr life
KHNP · Candu Energy · Ansaldo Nucleare
EPCM LIMITED NOTICE TO PROCEED
Cernavodă 3 & 4 — Completion
2 × 700+ MWe CANDU · ~€3.2bn EPCM
MILESTONE Construction FID pending · units targeted online 2030 (U3) and 2031 (U4)
Fluor · AtkinsRéalis · Ansaldo Nucleare · Sargent & Lundy
FID APPROVED
Doicești — NuScale VOYGR-6 SMR
6 × 77 MWe · 462 MWe total
MILESTONE FID approved by SNN shareholders Feb-26 · first module operational 2033
RoPower (SNN/Nova) · NuScale · Fluor
STRATEGY APPROVED
SNN Strategic Investment Programme
€20bn portfolio · horizon to 2035
MILESTONE 2025–2030 investment strategy approved by shareholders Sep-25
Nuclearelectrica (SNN) · Romanian Government
Source: Nuclearelectrica (SNN), World Nuclear Association, World Nuclear News, NucNet announcements, 23 June 2026. Cernavodă 3&4 construction FID is pending agreement of commercial terms.

## Slide 31
ROMANIA NUCLEAR PROGRAMME LANDSCAPE
Delivery Timeline, 2026–2037+
Operational / contracted construction
Licensing / engineering / pre-FID
Option / forward planning
2026
2028
2030
2032
2034
2036
2037+
Cernavodă Unit 1 — Refurbishment
650 MWe CANDU-6 · KHNP · Candu Energy · Ansaldo Nucleare · ~€1.9bn
Civil works begun Sep-25 · EC state aid request filed Jan-26
Outage/refurb phase, Dec-26 to Dec-28
Cernavodă 3 & 4 — Completion
2 × 700+ MWe CANDU · Fluor · AtkinsRéalis · Ansaldo · Sargent & Lundy · ~€3.2bn EPCM
EPCM Limited Notice to Proceed phase (24–30mo)
Units online 2030 (U3) and 2031 (U4)
Doicești — NuScale VOYGR-6 SMR
6 × 77 MWe (462 MWe) · RoPower (SNN/Nova) · NuScale · Fluor
FID approved by SNN shareholders, Feb-26
First module commercial operation, 2033
SNN Strategic Investment Programme
€20bn portfolio to 2035 · Nuclearelectrica (SNN) · Romanian Government
2025–2030 strategy approved by shareholders, Sep-25
€20bn investment horizon to 2035
TODAY
Source: Nuclearelectrica (SNN), World Nuclear Association, World Nuclear News, NucNet announcements, 23 June 2026. Cernavodă 3&4 construction FID is pending agreement of commercial terms; bar lengths illustrative.