5S Implementation Roadmap

PE-05e  |  Process Excellence  |  Fit For Nuclear Toolkit

A phased plan to take a site from first pilot to embedded, audited 5S

## Document control

| Version | Date | Author | Summary of change |
| --- | --- | --- | --- |
| 1.0 |  |  | First issue |

Document owner: ____________________        Status:  Draft / Issued        Next review date: ____________________

# 1.  Purpose

This roadmap sets out how to implement 5S workplace organisation across the site: from preparation and a single pilot area, through phased roll-out, to an embedded system sustained by audit, daily routine and leadership attention. It defines the phases, activities, outputs and exit criteria, the roles that make it work, and the measures that show it is working.

It is designed to be used with the rest of the PE-05 toolkit: the audit sheet and tracker (PE-05a), the training guide (PE-05b), printable red tags (PE-05c) and the area responsibility board (PE-05d). Together these provide the working evidence F4N verification expects: a 5S process that has been introduced deliberately and sustained through audit.

# 2.  Principles

- The area team does the 5S in its own area; facilitators support, they do not take over.

- Pilot first: prove the approach in one area, harvest the lessons, then roll out.

- Standardise and Sustain are part of the launch, not a later phase: the audit calendar and daily routine start the morning after the launch day.

- Every audit finding scored 1 or 2 becomes an owned action with a date.

- Recurring abnormalities are root-caused (PE-04), not repeatedly tidied.

- Progress is visible: scores, trends and before-and-after photos are published on area boards and reviewed in daily management (PE-03).

# 3.  Phased roadmap

Indicative durations assume one coordinator and a site of one to three production areas per phase wave; scale to suit. Do not start a new wave until the previous wave has passed two consecutive audits at 60 or above.

## Phase 0  |  Prepare

Typically 2 to 4 weeks

| Objectives | - Leadership aligned and committed - System ready before the first tag is raised |
| --- | --- |
| Key activities | - Appoint sponsor and 5S coordinator; agree the area map and wave plan - Train leadership and facilitators (PE-05b) - Set up red tags, holding area rules and disposition authority (PE-05c) - Prepare audit system, schedule and auditor pool (PE-05a) - Agree budget basics: labels, floor tape, shadow board materials, cleaning kit |
| Outputs / evidence | - Signed-off wave plan and area map - Trained facilitator list (skills matrix updated) - Red tag rules and holding area in place |
| Exit criteria | - Sponsor has communicated the why to the whole site - Pilot area and team selected and briefed |

## Phase 1  |  Pilot

Typically 4 to 6 weeks

| Objectives | - One area through all five Ss - A visible success story that sells the roll-out |
| --- | --- |
| Key activities | - Baseline photos from fixed viewpoints - Launch day: Sort (red tag sweep), Set in Order, Shine (PE-05b, slide guide) - Create photo standards, cleaning routine and area board (PE-05d) - First audits weekly; actions logged and closed (PE-05a) - Capture lessons: what to do differently in roll-out |
| Outputs / evidence | - Before-and-after photo set - Red tag disposition list with value recovered and space freed - Four weekly audit scores with closed actions - Pilot lessons-learned note |
| Exit criteria | - Two consecutive audits at 60+ with improving trend - Area team running its own routine without facilitator presence |

## Phase 2  |  Roll-out

Wave by wave, typically 6 to 12 weeks per wave

| Objectives | - Every production and support area through launch - Consistent site language: one labelling, marking and board standard |
| --- | --- |
| Key activities | - Repeat the pilot pattern wave by wave, using pilot team members as champions in new areas - Standardise materials and conventions site-wide (colours, label formats, min/max marks) - Extend to stores, goods in, maintenance, offices and shared drives (digital 5S) - Weekly audits per new area; monthly for areas past two clean audits |
| Outputs / evidence | - Area boards live in every launched area - Trend tracker populated for all areas (PE-05a) - Site standard for visual management documented |
| Exit criteria | - All planned areas launched and audited - Site average audit score at 60+ and rising |

## Phase 3  |  Embed

Typically 3 to 6 months after roll-out

| Objectives | - 5S woven into daily management, not running beside it - Standards maintained by routine, improved by audit |
| --- | --- |
| Key activities | - 5S score added as a standing KPI on SQDCP boards (PE-03) - Leadership area walks on a published rota - Recurring audit findings root-caused (PE-04) and standards updated (PE-06) - Auditor rotation refreshed; calibration session so scores stay consistent - Recognition rhythm: best area and most improved each quarter |
| Outputs / evidence | - SQDCP boards showing 5S KPI with actions - Closed root-cause investigations traced to audit findings - Recognition records and communications |
| Exit criteria | - Site average at 85+ (good) sustained for three consecutive months - Audits, actions and routines continue through holidays and busy periods without prompting |

## Phase 4  |  Sustain & improve

Ongoing

| Objectives | - Hold the standard and raise it - 5S maturity feeds the wider CI strategy and CSIP |
| --- | --- |
| Key activities | - Monthly audits as standard; spot audits by leadership - Annual refresh of photo standards and criteria as areas improve - Re-run Sort events after major product, layout or equipment changes - Feed 5S measures and savings into the CSIP and F4N evidence pack - Induct every new starter into the area standards (skills matrix) |
| Outputs / evidence | - Twelve-month trend per area with stable or rising scores - 5S contribution visible in CSIP project records - Maintained evidence pack for F4N verification and surveillance |
| Exit criteria | - None: this phase is the operating state. A falling trend triggers a return to the relevant earlier phase for that area. |

# 4.  Roles and governance

| Role | Responsibilities |
| --- | --- |
| Sponsor (senior leader) | Owns the why; communicates it; protects the time and small budget; walks areas; recognises teams. Reviews site trend monthly. |
| 5S coordinator | Runs the wave plan, audit schedule and materials; facilitates launch days; keeps PE-05a current; calibrates auditors; reports progress. |
| Area leader | Owns the area board, the routine and the actions; briefs the team; escalates blockers at the daily meeting. |
| Area team members | Run the daily routine in their zones; raise abnormalities; propose improvements; take part in audits of other areas. |
| Auditor pool | Trained team leaders and members who audit areas other than their own, to the published schedule, using the scoring guide. |

Governance rhythm: actions reviewed weekly at area level; site trend, stuck actions and recognition reviewed monthly at the management meeting; the roadmap itself reviewed quarterly against the exit criteria.

# 5.  Measures of success

- Audit score per area and site average (out of 125), trending in PE-05a

- Audit actions: number raised, % closed on time, oldest open action

- Search-time samples before and after launch (five standard retrieval tasks)

- Space freed and value recovered from red tag dispositions

- Safety signals: near misses and inspection findings in launched areas

- Mix-up, wrong-revision and missing-item defects in launched areas

# 6.  Risks and countermeasures

| Risk | Countermeasure |
| --- | --- |
| Launch energy fades after the blitz | Audit calendar and daily routine start immediately; sponsor walks monthly; scores published |
| Teams feel 5S is done to them | Area teams lead their own launch; facilitators support only; no outsider rearranges an area |
| Audits become a tick-box | Auditor rotation and calibration; leadership reviews the action log, not just the score; spot audits |
| Standards drift between areas | One site standard for labels, colours and boards, owned by the coordinator and checked in audits |
| Red tag holding area becomes a dumping ground | Named disposition authority and a decision date on every tag; holding area itself is audited |
| Production pressure squeezes the routine | Routines sized at minutes per day, not hours; 5S KPI on the SQDCP board keeps it visible when busy |

# 7.  Toolkit documents

- PE-05a  5S Audit Sheet & Tracker: scored audit, scoring guide, action log, trend tracker, schedule

- PE-05b  Training Guide: 5S Workplace Organisation: the full method, step by step

- PE-05c  5S Red Tags: printable tag pack for Sort events

- PE-05d  5S Area Responsibility Board: printable A3 board for every area

- Related: PE-03 performance boards (SQDCP), PE-04 problem solving and RCA, PE-06 standard operating procedures, PE-07 planned maintenance