## CSIP Master Plan
CONTINUOUS SUSTAINABLE IMPROVEMENT PLAN (CSIP)
Linked to strategic objectives. Review monthly at management review. Each action must have an owner, target, and measurable outcome.
Ref | Strategic Objective | CI Project / Action | Category | Owner | Start Date | Target Date | % Complete | Status | Measurable Target | Actual Outcome / Progress | Benefits Achieved | Notes
CI-001 | Nuclear Market Entry | Achieve and maintain F4N granting status | Nuclear Readiness | [Director] | [Date] | [Date] | 95 | Complete | F4N granted. NSS checklist score >85% | F4N granted [Quarter/Year]. Action plan closed out. | Nuclear customer pipeline developed
CI-002 | Operational Excellence | Implement lean manufacturing programme across all production cells - TIMWOODS waste analysis complete for each cell | Lean / Waste Reduction | [Ops Manager] | [Date] | [Date] | 60 | In Progress | Reduce identified waste by 25%. VSM completed for all cells. | VSMs completed for 3 of 5 cells. Cell 4 and 5 scheduled. | Estimated 15% cycle time reduction in Cells 1-3
CI-003 | Quality Performance | Reduce internal NCR rate from [X] per month to [Y] per month | Quality Improvement | [Quality Manager] | [Date] | [Date] | 40 | In Progress | NCR rate reduced by 50% within 12 months | NCR rate reduced by 22% to date. RCA programme embedded. | Reduced scrap and rework cost by approx. [£]
CI-004 | Delivery Performance | Improve OTIF from [X%] to 95% by end of year | Delivery / OTIF | [Ops Manager] | [Date] | [Date] | 70 | In Progress | OTIF 95% sustained for 3 consecutive months | OTIF at [X]% - up from [Y]% at start. Scheduling tool implemented. | Improved customer satisfaction score
CI-005 | People Development | Train all supervisors in structured problem solving (5 Whys, 8D, A3) | People / Culture | [HR Manager] | [Date] | [Date] | 100 | Complete | 100% of supervisors trained and assessed | All 8 supervisors completed training. 3 live projects underway. | 3 CI projects live using trained problem solving skills
CI-006 | Process Improvement | Implement 5S across all production areas and sustain with monthly audit | Process Improvement | [Ops Manager] | [Date] | [Date] | 75 | In Progress | 5S audit score >80% in all areas for 3 consecutive months | 5S implemented in machine shop and fabrication. Assembly area next. | Improved housekeeping; reduced search time; safer environment
CI-007 | Cost Reduction | Reduce energy consumption by 15% vs previous year baseline | Environmental | [Facilities] | [Date] | [Date] | 30 | In Progress | 15% energy reduction vs baseline year | Energy monitoring installed. LED lighting upgrade complete. | Estimated [£] saving per annum once complete
CI-008 | Quality Performance | Implement Statistical Process Control (SPC) for top 3 critical machining operations | Process Improvement | [Quality Manager] | [Date] | [Date] | 20 | In Progress | SPC charts live and reviewed weekly for 3 operations | SPC training complete. Chart design in progress. | Expected reduction in out-of-tolerance scrap
CI-009 | Customer Satisfaction | Introduce formal customer satisfaction survey and quarterly review process | Customer Satisfaction | [Sales Manager] | [Date] | [Date] | 50 | In Progress | Survey sent to all active customers quarterly. Score >8/10. | Survey designed and sent to 12 customers. Results being analysed. | Better insight into customer perception and loyalty
CI-010 | [Add strategic objective] | [Add CI action] |  |  |  |  | 0 | Not Started

## CI Project Register
CI PROJECT REGISTER
One row per CI project. Linked to CSIP. Review at monthly CI meeting. Benefits must be quantified where possible.
Project Ref | Project Title | CSIP Ref | Project Lead | Team Members | Start Date | Target Completion | Category | Problem Statement (one line) | Target Improvement (measurable) | Current Status | Benefits Realised
PROJ-001 | CNC Cell 3 Cycle Time Reduction | CI-002 | [Name] | [Team] | [Date] | [Date] | Lean / Waste Reduction | Set-up time on CNC Cell 3 averages 45 mins. Target: reduce to under 20 mins using SMED. | Set-up time <20 mins for 90% of changeovers | Improve | Set-up time reduced to avg 24 mins. Further improvement work planned.
PROJ-002 | Weld NCR Reduction - Fabrication Bay | CI-003 | [Name] | [Team] | [Date] | [Date] | Quality Improvement | Weld NCR rate is [X] per month, predominantly dimensional and fit-up issues. | NCR rate reduced by 50%. Root causes eliminated. | Analyse | Root cause identified as insufficient pre-weld inspection. New pre-weld check implemented.
PROJ-003 | 5S Machine Shop Implementation | CI-006 | [Name] | [Team] | [Date] | [Date] | Process Improvement | Machine shop 5S score at initial audit: 32%. Significant waste in searching for tools and consumables. | 5S audit score >80% sustained for 3 months | Control | Score now 78%. Sustaining phase commenced. Monthly audit in place.
PROJ-004 | On-Time Delivery Root Cause Analysis | CI-004 | [Name] | [Team] | [Date] | [Date] | Delivery / OTIF | OTIF at [X]%. Top 3 failure categories: material delays, rework, and scheduling conflicts. | OTIF 95% sustained for 3 consecutive months | Improve | Scheduling tool implemented. Material lead time buffer built into plan.

## Lessons Learned
LESSONS LEARNED LOG
Capture lessons from CI projects, NCRs, audits, and incidents. Share across the organisation. Feed into future projects and CSIP.
Lesson Ref | Date | Source (Project/NCR/Audit/Incident) | Category | What Happened | What We Learned | Recommended Change | Applied To | Shared With Team? | Date Shared
LL-001 | [Date] | PROJ-001 / CNC Changeover | Lean / Waste Reduction | SMED analysis revealed that 60% of set-up time was external work (fetching tools) that could be done while machine is still running. | External and internal set-up must be clearly separated before starting SMED improvements. Quick wins from moving external tasks first. | Create external set-up preparation checklist for all changeovers. Apply to all CNC cells, not just Cell 3. | Applied to Cells 1, 2, and 4 | Yes | [Date]
LL-002 | [Date] | NCR-003 / Weld Issue | Quality Improvement | Pre-weld dimension check was not on the ITP for this job type. Fit-up error only found post-weld. | ITP review process did not adequately cover fit-up as a hold point. Assumed it was checked but no formal record. | Add pre-weld dimensional hold point to all ITP templates for fabrication jobs. Cannot sign off weld without pre-weld record. | All ITP templates updated | Yes | [Date]
LL-003 | [Date] | CI-006 / 5S Machine Shop | Process Improvement | Initial 5S red-tag event removed 40% of items in the machine shop as either unused or in the wrong location. | Accumulation of unused items is gradual and invisible until a structured sort is carried out. Regular red-tag events needed. | Schedule a red-tag event for each area every 6 months as part of the 5S sustain programme. | Added to 5S audit schedule | Yes | [Date]

## Benefits Tracker
CI BENEFITS TRACKER
Quantify the impact of every completed CI project. Present at management review. Used as evidence of CI maturity at F4N verification.
Project Ref | Project Title | Date Completed | Category | Benefit Type | Baseline (Before) | Achieved (After) | Improvement % | Financial Saving (annual est. £) | Validated By
PROJ-001 | CNC Cell 3 Cycle Time Reduction | [Date] | Lean / Waste Reduction | Lead Time Reduction | 45 min avg changeover | 24 min avg changeover | 47% | [£ value] | [Manager Name]
PROJ-003 | 5S Machine Shop Implementation | [Date] | Process Improvement | Productivity Gain | 5S score 32%. High search time. | 5S score 78%. Search time reduced. | 145% | [£ value] | [Manager Name]
CI-005 | Supervisor Problem Solving Training | [Date] | People / Culture | Quality Improvement | No structured PS method | 3 live CI projects using 5 Whys / A3 | N/A (culture) | [£ value from projects] | [Manager Name]
[Add project]
TOTAL ESTIMATED ANNUAL FINANCIAL BENEFIT

## CI Meeting Agenda
MONTHLY CI REVIEW MEETING - STANDARD AGENDA AND RECORD
Complete before the meeting: update CSIP, project register, and benefits tracker. Circulate agenda 48 hours in advance.
Meeting Date
Chair
Attendees
Apologies
1. Review of Previous Meeting Actions
Review actions from last meeting. Confirm completed. Carry forward any outstanding.
2. CSIP Progress Review
Walk through CSIP Master Plan: % complete update for each action. Any items needing escalation?
3. CI Project Updates
Project lead to give 2-minute update on each active project: progress vs plan, blockers, next steps.
4. Lessons Learned Review
Any new lessons learned to share from completed projects, NCRs, or audits?
5. Benefits Tracker Update
Review financial and performance benefits from completed projects. Update tracker.
6. New CI Opportunities
Capture any new improvement ideas raised by team or from KPI review.
7. KPI Performance Review
Review headline KPIs vs targets: Quality (NCR, RFT), Delivery (OTIF), Safety (near misses). Any CI actions triggered?
8. Actions and Owners
Agree all actions from this meeting. Owner and due date for each.
9. Next Meeting Date
Confirm date, time, and location of next CI review meeting.
Actions from This Meeting
Action | Owner | Due Date