## Ideas Log
IDEAS AND SUGGESTIONS LOG
All ideas welcome. Every suggestion receives a response within 5 working days. Ideas that are implemented are recognised.
Idea Ref | Date Submitted | Submitted By | Department | Idea / Suggestion Description | Category | Potential Benefit | Priority | Review Date | Decision | Action Taken / Outcome | Status
IDEA-001 | [Date] | [Name] | Machine Shop | Move the angle grinders from the back of the machine shop to a dedicated grinding station near extraction. Currently carrying grinders across the shop floor which is a trip hazard and takes time. | Safety Improvement | Reduced trip hazard. Faster access to grinding. Better extraction compliance. | High | [Date] | Approved - To Implement | Grinding station created in Week [X]. Guards and extraction installed. Estimated 10 mins per day per operative saved. | Implemented
IDEA-002 | [Date] | [Name] | Quality | Create a pre-weld dimensional check sheet specific to each weld joint type so inspectors do not have to refer back to the drawing every time. Would reduce errors and speed up pre-weld checks. | Quality Improvement | Faster pre-weld inspection. Fewer missed checks. Reduced NCR rate on weld fit-up. | High | [Date] | Approved - To Implement | Check sheets created for top 5 weld joint types. Trialled for 2 weeks. Pre-weld NCR rate reduced. | Implemented
IDEA-003 | [Date] | [Name] | Stores | Put QR codes on material storage locations that link directly to the material entry in the traceability register. Would speed up material identification and reduce errors. | Digital / Technology | Faster material identification. Fewer traceability errors. | Medium | [Date] | Under Review | IT and Quality Manager reviewing feasibility and cost. Response due [date]. | Open
IDEA-004 | [Date] | [Name] | Fabrication | Provide a small whiteboard at each welding bay to record the current job number and drawing revision. This would avoid confusion when welders are moved between bays mid-job. | Quality Improvement | Reduced risk of welding wrong revision. Clearer bay identification. | Medium | [Date] | Approved - To Implement | Whiteboards installed in all 6 bays. Operatives briefed. | Implemented
IDEA-005 | [Date] | [Name] | Office | Switch from paper-based toolbox talk records to a simple tablet app. Would be easier to store records and search for historical training. | Digital / Technology | Faster records retrieval. Better evidence for audits. | Low | [Date] | Not Proceeding - See Reason | Paper records adequate for current volume. Digital solution to be considered as part of wider QMS review in [Year]. | Closed - Not Proceeding

## Idea Submission Form
IDEAS AND SUGGESTIONS SUBMISSION FORM
Submit your idea to your supervisor or the Quality Manager. All ideas are reviewed and you will receive a response within 5 working days.
Your Name (optional)
Department / Area
Date Submitted
Category of Idea | Safety / Quality / Cost / Productivity / Environmental / Other
Title of Your Idea
Description of Your Idea | Describe the idea or suggestion in detail. What is the current situation? What are you proposing? How would it work?
What benefit do you think this would bring?
Have you discussed this with your supervisor? | Yes / No
FOR MANAGEMENT USE ONLY
Idea Reference Assigned | IDEA-
Reviewed By
Date Reviewed
Decision | Approved to implement / Under further review / Not proceeding (reason below)
Reason if Not Proceeding
Feedback to Idea Submitter
Date Feedback Provided to Submitter

## Summary Dashboard
IDEAS AND SUGGESTIONS - SUMMARY DASHBOARD
Update this summary at the monthly CI review meeting. Present to all staff to demonstrate ideas are taken seriously.
KEY METRICS
Total Ideas Submitted (Year to Date)
Ideas Implemented
Ideas Under Review
Implementation Rate |  | %
Average Response Time (target: 5 days) | [Manual entry] | days
Ideas from Production
Safety Improvement Ideas
Quality Improvement Ideas
RECENT IMPLEMENTED IDEAS - SHARE WITH THE TEAM
Idea Ref | Submitted By | Description | Benefit Achieved