## Risk Register
HSE RISK ASSESSMENT REGISTER
Central register of all risk assessments. Update status when assessments are reviewed or new hazards identified.
RA Ref | Activity / Task | Area / Location | Hazard Category | Key Hazard Description | Initial Risk Rating | Additional Controls Applied | Residual Risk Rating | Review Due Date | Last Reviewed | Reviewed By | RA Document Ref | SSOW Required? | Status | Notes
RA-001 | CNC Machining Operations | Machine Shop | Machinery / Equipment | Contact with rotating cutting tools; ejected swarf; noise above 85dB(A) | HIGH | Full guarding; emergency stops; mandatory PPE; noise zones; operator training | MEDIUM | [Date] | [Date] | [Name] | RAMS-001 | Yes | Current
RA-002 | Manual Handling of Raw Material | Goods In / Stores | Manual Handling | Musculoskeletal injury from lifting steel billets; awkward load shapes | MEDIUM | Mechanical handling aids; team lift procedure; weight markings on all loads | LOW | [Date] | [Date] | [Name] | RAMS-002 | No | Current
RA-003 | Overhead Crane Operations | Machine Shop / Assembly | Lifting Operations | Falling loads; collision with persons; structural failure of lifting equipment | HIGH | LOLER inspection; operator certification; exclusion zones; slinging training | MEDIUM | [Date] | [Date] | [Name] | RAMS-003 | Yes | Current
RA-004 | Welding and Hot Work | Fabrication Bay | Hot Work | Arc flash; UV radiation; fume inhalation; fire; burns | HIGH | Hot work permit; LEV; screens; qualified welders; fire watch; RPE | MEDIUM | [Date] | [Date] | [Name] | RAMS-004 | Yes | Current
RA-005 | Chemical Storage and Handling (COSHH) | Chemical Store | COSHH / Hazardous Substances | Skin and respiratory sensitisation; spillage; fire/explosion risk | MEDIUM | COSHH assessments; MSDS; spill kit; LEV; PPE; secondary containment | LOW | [Date] | [Date] | [Name] | RAMS-005 | No | Current
RA-006 | Display Screen Equipment (DSE) Use | Office | DSE / Ergonomics | Musculoskeletal disorders; eye strain; stress from prolonged DSE use | LOW | DSE assessments completed; adjustable workstations; regular breaks encouraged | LOW | [Date] | [Date] | [Name] | RAMS-006 | No | Current
RA-007 | Electrical Maintenance Work | Throughout Site | Electrical | Electrocution; arc flash; fire from live working | HIGH | Competent persons only; LOTO; test before touch; permit to work for live work | MEDIUM | [Date] | [Date] | [Name] | RAMS-007 | Yes | Due for Review
RA-008 | Forklift Truck Operations | Yard / Warehouse | Machinery / Equipment | Collision with pedestrians; overturning; falling loads; crush injuries | HIGH | Segregated pedestrian routes; licenced operators; speed limits; load limits | MEDIUM | [Date] | [Date] | [Name] | RAMS-008 | Yes | Current

## Hazard Log
NEAR MISS, HAZARD, AND UNSAFE ACT LOG
Record all near misses, hazards, and unsafe acts. All entries must be investigated and closed. This log feeds into the monthly safety review.
Log Ref | Date Reported | Reported By | Type | Location | Description of Near Miss / Hazard / Unsafe Act | Immediate Action Taken | Root Cause | Corrective Action Required | Action Owner | Due Date | Status
NM-001 | [Date] | [Name] | Near Miss | Machine Shop | Operative slipped on cutting fluid on floor near CNC 3. No injury. Area was not cleaned after fluid leak. | Area cleaned immediately; warning signs placed; fluid leak repaired | Inadequate housekeeping routine; no regular inspection of fluid containment | Add daily floor inspection to housekeeping checklist; repair containment tray on CNC 3 | [Name] | [Date] | Closed
NM-002 | [Date] | [Name] | Unsafe Act | Fabrication Bay | Operative observed welding without welding fume RPE. Stated "it was only a short weld". | Work stopped; operative reminded of PPE requirement; RPE provided | Insufficient awareness of welding fume requirements following 2019 HSE guidance update | Toolbox talk on welding fume to all fabrication staff; RPE compliance added to daily inspection | [Name] | [Date] | Closed
NM-003 | [Date] | [Name] | Hazard Identified | Yard | Forklift pedestrian crossing marking faded and no longer clearly visible. Near-miss between FLT and pedestrian. | Crossing resprayed with high-visibility paint; temporary barriers erected | Planned maintenance programme did not include yard markings inspection | Add yard marking condition to quarterly site inspection checklist | [Name] | [Date] | Open

## COSHH Register
COSHH REGISTER
Control of Substances Hazardous to Health. All hazardous substances used on site must be listed here. COSHH assessment required before use.
Ref | Product Name | Supplier | Location Used / Stored | Hazard Classification | Exposure Route | WEL / Exposure Limit | PPE Required | Substitution Possible? | MSDS Available? | COSHH Assessment Ref | Review Date
C-001 | Cutting / Coolant Fluid (Soluble Oil) | [Supplier] | Machine Shop | Skin / respiratory sensitiser; potential carcinogen (mist) | Skin contact; inhalation of mist | WEL: 1mg/m3 (PNOR respirable) | Nitrile gloves; RPE (FFP2 min); eye protection | No - required for process | Yes | COSHH-001 | [Date]
C-002 | Welding Fume (all types) | N/A (process generated) | Fabrication Bay | Carcinogen (Group 1 IARC); sensitiser | Inhalation | WEL: varies by fume type | P3 FFP3 or supplied air; LEV mandatory | No - intrinsic to process | Yes (SDS for consumables) | COSHH-002 | [Date]
C-003 | Degreasing Solvent (e.g. Acetone) | [Supplier] | Cleaning Area | Flammable; skin defatting; CNS depressant at high concentrations | Skin; inhalation; ingestion | WEL: 1210mg/m3 (8hr TWA) | Nitrile gloves; eye protection; ensure ventilation | Consider aqueous alternative | Yes | COSHH-003 | [Date]
C-004 | Spray Paint / Coating | [Supplier] | Spray Booth | Flammable; sensitiser; VOCs | Inhalation; skin contact | WEL: substance specific | RPE (A1P2 minimum); chemical gloves; eye protection; overalls | Assess for water-based alternative | Yes | COSHH-004 | [Date]
C-005 | Battery Acid (Lead-Acid Batteries) | [Supplier] | Battery Store | Corrosive; H2SO4 | Skin; eyes; inhalation of acid mist | Corrosive: immediate effect | Acid-resistant gloves; face shield; acid-resistant apron | No - operational requirement | Yes | COSHH-005 | [Date]

## Review Schedule
RISK ASSESSMENT REVIEW SCHEDULE
All risk assessments must be reviewed at least annually, or following any incident, near miss, or significant change to the activity.
RA Ref | Activity / Task | Review Frequency | Last Review Date | Next Review Due | Reviewer | Review Outcome | Action Required | Status
RA-001 | CNC Machining Operations | Annual | [Date] | [Date] | [Name] | No Change Required | None | Complete
RA-002 | Manual Handling of Raw Material | Annual | [Date] | [Date] | [Name] | Minor Update | Updated load weight limits on traceability labels | Complete
RA-003 | Overhead Crane Operations | 6 Monthly | [Date] | [Date] | [Name] | No Change Required | None | Complete
RA-004 | Welding and Hot Work | Annual | [Date] | [Date] | [Name] | Significant Revision Required | Update for 2019 HSE welding fume guidance; add RPE requirements | In Progress
RA-005 | Chemical Storage and Handling | Annual | [Date] | [Date] | [Name] | No Change Required | None | Scheduled
RA-006 | DSE Use | Annual | [Date] | [Date] | [Name] | No Change Required | None | Complete
RA-007 | Electrical Maintenance Work | Annual | [Date] | [Date] | [Name] | Minor Update | Updated competency requirements; added arc flash section | Overdue
RA-008 | Forklift Truck Operations | Annual | [Date] | [Date] | [Name] | No Change Required | None | Complete

## Instructions
QHSE-HSE-02: RISK ASSESSMENT REGISTER - USER GUIDE
Purpose | This register is the central record of all HSE risk assessments in force at the company. Every risk assessment should appear in Sheet 1. The register gives management visibility of risk levels across the site and ensures no assessment is missed or overdue.
Sheet 1: Risk Register | The master list. Add a row for each risk assessment. Update the residual risk rating after controls are applied. Review due dates must be monitored monthly.
Sheet 2: Hazard Log | Record every near miss, hazard, and unsafe act here. All entries must be investigated. Closed entries provide evidence of a proactive safety culture for the F4N verification and ISO 45001 audits.
Sheet 3: COSHH Register | All substances hazardous to health must be listed. A COSHH assessment is required before any new substance is used. MSDS sheets must be stored and accessible at the point of use.
Sheet 4: Review Schedule | Tracks when each RA is due for review. Reviews must happen at least annually or following any incident, near miss, or significant change. Overdue RAs are highlighted red.
Legal Basis | Risk assessments are required by the Management of Health and Safety at Work Regulations 1999 (Reg 3). COSHH assessments are required by the COSHH Regulations 2002. LOLER assessments for lifting equipment. PUWER assessments for work equipment. This register supports compliance with all of these.
F4N Assessor Note | At the F4N verification visit, the assessor will want to see this register as evidence of systematic risk management. They will also look at the Hazard Log to assess safety culture. Ensure all entries are current and overdue reviews are addressed before any verification visit.