## Annual Audit Schedule
ANNUAL HSE INTERNAL AUDIT SCHEDULE
Plan all internal HSE audits for the year. Update actual dates as audits are completed. Report to management review.
Audit Ref | Audit Type | Scope / Area | Audit Standard / Criteria | Lead Auditor | Planned Q1 | Planned Q2 | Planned Q3 | Planned Q4 | Actual Date Completed | Audit Report Ref | Findings Summary | Status
AUD-001 | Full HSE System Audit | All departments | ISO 45001:2018 / HSG65 | [Lead Auditor] | Jan |  |  |  | [Date] | RPT-001 | No major non-conformances. 3 OFIs raised. | Complete
AUD-002 | Risk Assessment Review | Manufacturing | Management of H&S at Work Regs 1999 | [Lead Auditor] |  | Apr |  |  | [Date] | RPT-002 | 2 RAs overdue for review. Actions raised. | Complete
AUD-003 | COSHH Compliance Audit | Chemical Store / Machine Shop | COSHH Regulations 2002 | [Lead Auditor] |  |  | Jul |  |  |  |  | Scheduled
AUD-004 | Fire Safety Audit | Whole Site | Regulatory Reform (Fire Safety) Order 2005 | [Lead Auditor] |  |  | Aug |  |  |  |  | Scheduled
AUD-005 | SSOW and PTW Compliance Audit | High Risk Areas | Internal SSOW Procedure | [Lead Auditor] |  |  |  | Oct |  |  |  | Scheduled
AUD-006 | Electrical Safety Audit | Throughout Site | Electricity at Work Regs 1989 / PUWER | [Lead Auditor] |  |  |  | Nov |  |  |  | Scheduled
AUD-007 | LOLER / Lifting Equipment Audit | Machine Shop / Yard | LOLER 1998 | [Lead Auditor] |  |  |  | Dec |  |  |  | Scheduled
AUD-008 | Environmental Compliance Audit | Whole Site | ISO 14001:2015 / Environmental Permitting | [Lead Auditor] | Mar |  |  |  | [Date] | RPT-003 | 1 non-conformance: waste manifest records incomplete. Action closed. | Complete

## Audit Report Template
HSE INTERNAL AUDIT REPORT
Complete one report per audit. File with audit schedule. Present findings at management review.
AUDIT IDENTIFICATION
Audit Reference | AUD-
Audit Type / Title
Audit Standard / Criteria
Scope and Areas Audited
Audit Date(s)
Lead Auditor
Other Auditors (if any)
Auditee / Area Manager
Report Date
Report Status | Draft / Final
AUDIT SUMMARY AND SCORING
Score each area from 0-10. 0 = No system in place. 5 = Partial compliance. 10 = Full compliance. Any score below 7 requires an action.
Audit Area | Score (0-10) | Finding Summary | RAG Status
Risk Assessment and RAMS documentation
COSHH Controls and Register
Safe Systems of Work (SSOW) / PTW compliance
PPE provision, condition, and usage
Machinery and equipment safety (guarding, PUWER)
Lifting equipment (LOLER compliance)
Electrical safety
Fire safety and emergency arrangements
Housekeeping and environmental controls
Incident, near miss, and hazard reporting
Training records and competency management
Management review and QHSE KPI monitoring
FINDINGS AND ACTIONS
Finding Ref | Type | Description of Finding | Requirement / Standard | Risk Level | Recommended Action | Action Owner | Due Date | Status
AUDIT SIGN OFF
Lead Auditor: Name / Signature / Date
Auditee / Manager: Name / Signature / Date
H&S Manager: Name / Signature / Date
Presented at Management Review: Date / Meeting Reference

## Findings Tracker
AUDIT FINDINGS AND ACTIONS TRACKER
All audit findings across all audits. Close all actions before the next audit in the same area. Present at management review.
Finding Ref | Audit Ref | Date Raised | Type | Area / Department | Description | Required Action | Action Owner | Due Date | Date Closed | Evidence of Closure | Status
F-001 | AUD-001 | [Date] | Minor NC | Machine Shop | Risk assessment RA-007 (Electrical Maintenance) was overdue for annual review by 3 months. | Complete review of RA-007 and update register. Confirm completion in RA review schedule. | [Name] | [Date] | [Date] | Updated RA-007 filed in system; register updated | Closed
F-002 | AUD-001 | [Date] | Observation | Stores | COSHH data sheets (MSDS) for 2 substances not accessible at point of use. | Print current MSDS for all substances and laminate at point of use. Add to COSHH register. | [Name] | [Date] | [Date] | MSDS sheets posted in chemical store and at mixing stations | Closed
F-003 | AUD-002 | [Date] | OFI | Fabrication Bay | Welding fume RPE inspection records not consistently completed. Operatives wearing RPE but record sheet not signed. | Brief team on RPE inspection record requirement. Add RPE inspection to daily supervisor check. | [Name] | [Date] |  |  | Open
F-004 | AUD-003 | [Date] | Major NC | Chemical Store | No COSHH assessment for new degreasing solvent introduced 3 months ago. | Complete COSHH assessment immediately. Suspend use of product until assessment is complete. | [Name] | [Date] |  |  | In Progress

## Audit Programme Guidance
QHSE-HSE-04: INTERNAL HSE AUDIT PROGRAMME - GUIDANCE
Legal Basis | Internal audits of your health and safety management system are required by ISO 45001:2018 (clause 9.2) and represent good practice under HSG65. The Management of Health and Safety at Work Regulations 1999 (Regulation 5) requires arrangements for monitoring and review of preventive and protective measures.
Audit Frequency | The whole HSE management system must be audited at least once per year. High-risk areas (machine shop, fabrication, chemical handling) should be audited every 6 months. Targeted audits must be conducted following any significant incident, near miss, or regulatory change.
Auditor Independence | Internal auditors must not audit their own area of work. Where the company is too small to achieve full independence, document the limitation and ensure the audit is reviewed by senior management. External auditors may be used for the annual full system audit.
Auditor Competence | Lead auditors should hold IOSH or equivalent H&S qualification and have completed internal auditor training (ISO 45001 internal auditor course recommended). Audit records must show the auditor's name and qualifications.
Audit Evidence | Auditors must collect objective evidence (documents, records, observations, interviews) for every finding. Opinion-based findings are not acceptable. Evidence must be specific: reference document numbers, dates, names, and observations.
Non-Conformance Grading | Major NC: complete failure to comply with a requirement; significant risk of harm or legal non-compliance. Minor NC: partial or inconsistent compliance; limited risk. Observation: potential issue; no immediate risk. OFI: opportunity to improve beyond current compliance.
F4N Verification | The F4N assessor will ask to see the audit schedule, completed audit reports, and the findings tracker showing actions closed. Ensure all overdue actions are addressed before any verification visit. The audit programme itself is evidence of a systematic approach to HSE management.
Management Review | Audit results must be presented at the management review meeting. Senior leadership must demonstrate they have reviewed findings and approved resource for corrective actions. Management review minutes referencing audit findings are key evidence for both F4N and ISO 45001.