## Plan Register
QUALITY PLAN REGISTER
Central register of all quality plans issued. Update status as plans progress through the lifecycle.
QP Ref | Contract / Project Title | Customer | Contract Value (approx) | Nuclear Classification | Quality Manager | Date Submitted | Customer Accepted (Y/N) | Acceptance Ref | ITP Ref | LQR Status | Current QP Status | Date Closed | Notes
QP-001 | [Contract / Project Title] | [Customer Name] | [Value] | QC2 | [Name] | [Date] | Yes | [Ref] | ITP-001 | In Progress | In Progress
QP-002 | [Contract / Project Title] | [Customer Name] | [Value] | QC3 | [Name] | [Date] | Yes | [Ref] | ITP-002 | Not Started | Accepted
QP-003 | [Contract / Project Title] | [Customer Name] | [Value] | Non-Nuclear | [Name] | [Date] | Pending |  | ITP-003 | Not Started | Submitted

## Status Tracker
QUALITY PLAN STATUS TRACKER
Track each plan through key lifecycle milestones. Green = complete. Amber = in progress. Red = overdue.
QP Ref | Customer | Plan Drafted | Draft Reviewed Internally | Submitted to Customer | Customer Accepted | Opening Meeting Held | ITP Accepted | Work Started | Mid-Contract Review | Final Inspection Complete | LQR Submitted | LQR Accepted | Plan Closed
[Ref] | [Customer]
[Ref] | [Customer]
[Ref] | [Customer]
[Ref] | [Customer]
[Ref] | [Customer]
[Ref] | [Customer]
[Ref] | [Customer]
[Ref] | [Customer]
[Ref] | [Customer]
[Ref] | [Customer]

## Hold Point Tracker
ITP HOLD POINT TRACKER
Log all hold and witness points. Work must not proceed past a Hold Point until signed off by both Inspector and Customer QR.
QP Ref | ITP Act. Ref | Phase | Activity Description | Type (H/W) | Notification Date Sent | Customer Notified (Y/N) | Planned Date | Actual Date | Inspector Attended | Customer QR Attended | Result (Pass/Fail) | Sign Off Ref | Notes / Issues
QP-001 | 0.1 | Pre-Production | Quality Plan submitted and accepted | H | [Date] | Yes | [Date] | [Date] | Yes | Yes | Pass | [Ref]
QP-001 | 0.4 | Pre-Production | Special process procedures accepted | H | [Date] | Yes | [Date] | [Date] | Yes | Yes | Pass | [Ref]
QP-001 | 1.2 | Goods Receipt | Material certificate review | H | [Date] | Yes | [Date] |  |  |  | Pending |  | Awaiting materials
QP-001 | 2.1 | Manufacture | Pre-weld inspection | H |  | No | [Date] |  |  |  | Pending |  | Scheduled
QP-001 | 2.3 | Manufacture | Post-weld visual inspection | H |  | No | [Date] |  |  |  | Pending

## Document Submission Log
DOCUMENT SUBMISSION LOG
Track all quality documents submitted to the customer for review, approval, or acceptance.
Log Ref | QP Ref | Document Title | Document Ref | Revision | Date Submitted | Submitted By | Customer Recipient | Review Required By | Customer Decision | Customer Comments | Revision Required | Resubmission Date | Status
SUB-001 | QP-001 | Contract Quality Plan | QP-001-Rev A | A | [Date] | [Name] | [Customer QR] | [Date] | Accepted | No comments | No |  | Accepted
SUB-002 | QP-001 | Inspection and Test Plan | ITP-001-Rev A | A | [Date] | [Name] | [Customer QR] | [Date] | Accepted with Comments | See attached review | Yes | [Date] | Accepted
SUB-003 | QP-001 | Welding Procedure WPS-001 | WPS-001-Rev 1 | 1 | [Date] | [Name] | [Customer QR] | [Date] | Under Review |  |  |  | Under Review

## Lessons Learned
QUALITY PLAN LESSONS LEARNED LOG
Record lessons from completed contracts to improve quality planning on future work.
Ref | QP Ref / Contract | Lesson Category | What Happened | Impact | Root Cause | Lesson Learned | Recommended Change to QP Template | Implemented in Template? | Date | Owner
LL-001 | QP-001 / [Contract] | Documentation Gap | Material certificates not received before work started; caused delay at hold point | Hold point delayed by 3 days; programme impact | Material cert requirement not explicit enough in QP Section 6 | Material cert receipt must be verified as a gate before goods receipt inspection can be signed off | Add explicit material cert check to Section 6 and ITP Phase 1 | Yes | [Date] | [Name]
LL-002 |  | NCR / Non-Conformance

## Instructions
QHSE-QP-03: QUALITY PLAN REGISTER AND STATUS TRACKER - USER GUIDE
Purpose | This workbook is the central management tool for tracking all quality plans issued by your organisation. It connects the quality plan lifecycle from initial drafting through to contract close and lessons learned. One row per contract quality plan should be maintained in the Plan Register.
Sheet 1: Plan Register | The master list of all quality plans. Add a new row for each new contract. Update the status column as the plan progresses. This sheet gives management visibility of all live quality plans at a glance.
Sheet 2: Status Tracker | Milestone-by-milestone view of each plan. Use the dropdown to mark each milestone as Complete, In Progress, Not Started, N/A, or Overdue. Colour coding updates automatically. Review this sheet at your regular quality meetings.
Sheet 3: Hold Point Tracker | Log every hold and witness point across all live ITPs. Record notification dates, actual dates, attendance, and results. This sheet is your audit trail for customer hold point compliance. Update in real time during manufacture.
Sheet 4: Document Submission Log | Track every document submitted to the customer for acceptance. Record the decision and any revision requirements. Resubmit rejected documents and update the status. This log is evidence of your document control process.
Sheet 5: Lessons Learned | After each contract closes, record lessons from the quality plan process. This is a continuous improvement tool. Review lessons before starting a new quality plan to avoid repeating the same issues.
Nuclear Sector Note | For QC1 and QC2 contracts, this register should be reviewed monthly by the Quality Manager and presented at the quarterly management review. Evidence of active quality plan management is a key assessor requirement at the F4N verification visit and at any customer audits.