QUALITY PLANNING PROCESS GUIDE

How We Develop, Issue, and Manage Quality Plans

[Company Name]

| Document Reference: | QMS-QP-PROC-001 |
| --- | --- |
| Version: | 1.0 |
| Issue Date: | [DD/MM/YYYY] |
| Review Date: | [DD/MM/YYYY] |
| Document Owner: | Quality Manager |
| Approved By: | Managing Director |
| Classification: | Commercial in Confidence |

1. Purpose and Scope

1.1 Purpose

This process guide defines how [Company Name] develops, issues, manages, and closes quality plans for contracts and projects. It sets out who is responsible for each stage of the quality planning process, what must be included in a quality plan, and how the process links to the Inspection and Test Plan (ITP) and Lifetime Quality Record (LQR).

Following this process ensures that quality requirements are understood, planned, and controlled from contract award through to final delivery, and that all relevant evidence is captured and retained.

1.2 Scope

This guide applies to all contracts and projects where a quality plan is required. This includes:

All contracts with nuclear customers or involving nuclear safety-classified items.

All contracts where the customer's purchase order or specification requires a quality plan or ITP.

Any contract where the Quality Manager determines that the scope, complexity, or risk warrants a formal quality plan.

Where a contract is straightforward and low-risk, the Quality Manager may determine that a simplified quality plan is appropriate. This judgement must be documented.

1.3 Relationship to Other Documents

| Document | Purpose | Reference |
| --- | --- | --- |
| Contract Quality Plan Template | Standard template used to produce all quality plans | QHSE-QP-01 |
| Inspection and Test Plan (ITP) | Defines all inspection activities, hold and witness points | QHSE-QP-02 |
| Quality Plan Register and Status Tracker | Central management tool for all live quality plans | QHSE-QP-03 |
| Non-Conformance Procedure | Defines how non-conformances are raised and managed | [Company Ref] |
| CFSI Procedure | Defines controls for counterfeit and suspect items | [Company Ref] |
| Document Control Procedure | Defines how documents are controlled and distributed | [Company Ref] |
| ISO 9001:2015 | QMS standard: clauses 8.1, 8.5.1, and 8.6 are most relevant | External Standard |
| ISO 19443:2018 | Nuclear-specific QMS requirements where applicable | External Standard |

2. The Quality Planning Process

2.1 Overview

Quality planning is not a one-off document exercise. It is an active process that runs for the full life of a contract, from pre-award preparation through to final delivery and lessons learned. The diagram below shows the key stages.

| Stage | Stage Title | Description | Responsible |
| --- | --- | --- | --- |
| Stage 1 | Contract Award and Trigger | Quality Manager reviews contract/PO requirements and determines if a quality plan is needed. A trigger exists if the customer requires it, if nuclear safety classification applies, or if the Quality Manager judges it necessary. | Contract Manager, Quality Manager |
| Stage 2 | Quality Plan Preparation | Quality Manager drafts the Quality Plan using the standard template (QHSE-QP-01). All sections must be completed including: contract details, applicable standards, roles and responsibilities, document control, materials and traceability, inspection strategy, NCR process, and change control. | Quality Manager |
| Stage 3 | Internal Review and Approval | Draft Quality Plan reviewed internally by the Contract Manager and, where applicable, any specialist leads (welding, NDT). Comments resolved. Quality Plan approved by the Contract Manager. | Quality Manager, Contract Manager |
| Stage 4 | ITP Preparation | Inspection and Test Plan prepared alongside or immediately after the Quality Plan, referencing the same document standards. ITP identifies all inspection activities, hold and witness points, acceptance criteria, and required records. | Quality Manager, Lead Inspector |
| Stage 5 | Submission to Customer | Quality Plan and ITP submitted to the customer for acceptance. Record submission in the Document Submission Log (QHSE-QP-03 Sheet 4). Work shall not commence until written customer acceptance is received. | Quality Manager |
| Stage 6 | Opening Meeting | A contract opening / kick-off meeting is held with the customer to confirm understanding of requirements, agree on hold and witness point notification timescales, and confirm SQEP for key roles. | Contract Manager, Quality Manager, Customer QR |
| Stage 7 | Execution and Monitoring | Quality plan is live. Inspector executes ITP activities. Hold and witness points are notified and signed off. NCRs are raised and managed. Quality Manager monitors progress and produces regular quality status reports. | Quality Manager, Lead Inspector |
| Stage 8 | Change Control | Any proposed changes to scope, drawings, or specifications are assessed for impact on the Quality Plan and ITP. Changes are submitted to the customer for approval before implementation. | Quality Manager, Contract Manager |
| Stage 9 | Final Inspection and LQR | Final inspection activities completed and signed off. LQR package assembled and reviewed against the QP Section 12 checklist. Certificate of Conformity issued. LQR submitted to the customer. | Quality Manager, Lead Inspector |
| Stage 10 | Contract Close and Lessons Learned | Quality Plan formally closed in the register. Post-contract lessons learned review held. Any improvements to the quality plan template or process are recorded and implemented. | Quality Manager, Contract Manager |

3. What Must Be in a Quality Plan

3.1 Mandatory Content

Every quality plan produced by [Company Name] must include the following sections as a minimum. Use the Contract Quality Plan Template (QHSE-QP-01) which contains all required sections.

| Section | Content Required | Why It Is Required |
| --- | --- | --- |
| Document Control | Version history, distribution list, related documents | Ensures the right version is used by all parties |
| Contract Overview | Contract details, scope of supply, customer requirements | Defines exactly what the quality plan covers |
| Quality Objectives | Measurable objectives for this contract (RFT rate, NCR targets, etc.) | Gives the team clear quality targets to work to |
| Applicable Standards | All drawings, specifications, codes, and standards that govern the work | Ensures nothing is missed; forms basis for acceptance criteria |
| Organisation and Responsibilities | Named SQEP for all quality roles; communication plan | Accountability is clear; customer knows who to contact |
| Document and Records Control | How documents and LQR records will be managed | Nuclear requirement: traceability and record integrity |
| Materials and Traceability | Procurement controls, certification requirements, CFSI checks | Material traceability is a fundamental nuclear requirement |
| Manufacture and Process Control | Controls for manufacturing, special processes, and process qualification | Ensures work is carried out correctly and to specification |
| Inspection and Testing | Reference to ITP; hold/witness point strategy; MTE calibration | Defines how conformance will be demonstrated |
| Non-Conformance Control | NCR process; disposition options; customer notification requirements | Controls non-conforming work; provides audit trail |
| Change Control | Process for managing changes to scope, specs, or the QP itself | Nuclear requirement: change must be controlled and approved |
| Sub-Contractor Control | How sub-contractors are selected, managed, and quality requirements flowed down | Company retains responsibility for all sub-contracted work |
| Final Inspection and Delivery | Final inspection checklist; LQR package requirements; CoC issue | Confirms product meets requirements before release |
| Sign Off | Customer acceptance signature block | Formal confirmation that customer has accepted the plan |

3.2 Scaling the Quality Plan to the Contract

The depth and detail of a quality plan should reflect the nuclear safety classification and complexity of the contract. The following guide applies:

| Nuclear Classification | Quality Plan Depth | ITP Hold Points | LQR Requirements |
| --- | --- | --- | --- |
| QC1 | Full quality plan. All sections completed in full. Customer witness at all major stages. | Mandatory hold points at every critical manufacturing stage; 100% customer witness | Full LQR including all certs, weld records, NDT reports, 100% dimensional records |
| QC2 | Full quality plan. Customer hold points at key manufacturing stages. | Hold points at pre-weld, post-weld, NDT, and final inspection; 50% witness | Full LQR; key inspection records and certificates |
| QC3 | Standard quality plan. Customer notified of hold points. | Witness points at key stages; hold points at final inspection | LQR with key records; certificates of conformity |
| QC4 / Non-Nuclear | Simplified quality plan may be acceptable. Discuss with customer. | Review points; certificate of conformity at delivery | Certificates of conformity and delivery documentation |

4. Hold Points and Witness Points

4.1 Definitions and Rules

HOLD POINT: A point in the manufacturing or inspection sequence beyond which work MUST NOT proceed without the physical presence and formal sign-off of the designated inspector, and where required, the Customer Quality Representative. This is a hard stop. Work cannot continue until the hold point is formally cleared.

WITNESS POINT: A point at which the customer has been formally notified and has the right to attend. If the customer does not attend after receiving the required notice period, work may proceed. The notification and the customer response (or non-response) must be documented.

4.2 Notification Requirements

The following minimum notification periods apply for hold and witness points:

| Classification | Hold Point Notice to Customer | Witness Point Notice to Customer | Out-of-Hours Notification |
| --- | --- | --- | --- |
| QC1 | 10 working days minimum | 10 working days minimum | Emergency contact details required in QP Section 4 |
| QC2 | 5 working days minimum | 5 working days minimum | Notify Contract Manager if activity falls outside business hours |
| QC3 | 3 working days minimum | 3 working days minimum | Standard business hours |
| QC4 / Non-Nuclear | As agreed with customer | As agreed with customer | As agreed |

All notifications must be in writing (email is acceptable). The notification must state: the ITP activity reference, the planned date and time, the location, the name of the attending inspector, and the documents that will be available at the activity.

4.3 If the Customer Fails to Attend a Hold Point

If the customer fails to attend a hold point after receiving the required written notice:

Contact the Customer Quality Representative immediately to confirm the situation.

Do not proceed without written authorisation from the customer to continue past the hold point.

Document the notification sent, the customer's response (or lack of response), and any authorisation to proceed.

Raise the issue with the Contract Manager if authorisation is not received within 24 hours.

Under no circumstances should work proceed past a hold point without either the customer being present and signing off the activity, or the customer providing written authorisation to proceed in their absence. This is a fundamental requirement of nuclear supply chain quality management.

5. Non-Conformance Management

5.1 When to Raise an NCR

A Non-Conformance Report (NCR) must be raised whenever any product, material, service, or activity does not comply with the specified requirements. This includes:

Dimensional or visual characteristics outside drawing tolerance.

Material certificates that do not meet the specified standard.

Weld defects identified during visual or NDT inspection.

Any deviation from an approved procedure or method statement.

Items suspected of being counterfeit, fraudulent, or suspect (CFSI).

Any activity that has proceeded past a hold point without proper sign-off.

5.2 NCR Disposition Options

| Disposition | Definition | Customer Approval Required? | When to Use |
| --- | --- | --- | --- |
| Rework | Non-conforming item is reworked to fully meet the specified requirements | No (unless rework affects approved procedures) | Item can be made to comply through additional work that does not change the design |
| Repair | Item is repaired but will not fully conform to the original specification after repair | YES - always | Item cannot be made to fully conform but can be repaired to an acceptable alternative standard |
| Use As Is | Item is accepted in its non-conforming state without any modification | YES - always | Non-conformance is minor and does not affect form, fit, function, or safety |
| Scrap | Item is scrapped and replaced | No | Item cannot be reworked, repaired, or used; or the cost of rework exceeds replacement cost |

5.3 Customer Notification

The following NCRs must be notified to the customer:

All NCRs on QC1 items: within 24 hours of raising.

All NCRs on QC2 items that affect form, fit, function, or customer delivery: within 24 hours.

Any NCR where the proposed disposition is Repair or Use As Is: before work continues.

Any NCR that may indicate a systemic quality issue: immediately.

6. Materials Control and CFSI

6.1 Material Certification Requirements

The required level of material certification depends on the nuclear safety classification of the contract. The following standards apply:

| Classification | Minimum Certification Level | Additional Requirements |
| --- | --- | --- |
| QC1 | BS EN 10204 Type 3.2 (witnessed by accredited inspection body) | Full material traceability matrix; certificates checked by Quality Manager |
| QC2 | BS EN 10204 Type 3.1 (manufacturer's authorised signatory) | Certificates verified against specification; traceability matrix maintained |
| QC3 | BS EN 10204 Type 2.2 (manufacturer's test report) | Certificates filed; checked against specification |
| QC4 / Non-Nuclear | BS EN 10204 Type 2.1 (declaration of compliance) minimum | As specified by customer |

6.2 CFSI Controls

Counterfeit, Fraudulent, and Suspect Items (CFSI) represent a serious risk in the nuclear supply chain. The following controls must be applied on all contracts covered by a quality plan:

All materials and components must be sourced from approved suppliers on the company Approved Supplier List.

CFSI inspection must be carried out at goods receipt for all incoming materials and components.

Warning signs of CFSI include: pricing significantly below market rate; unusual packaging or markings; certificates that look altered or inconsistent; supplier reluctance to provide original documentation.

Any item suspected of being CFSI must be quarantined immediately, tagged with a CFSI suspect label, and the Quality Manager notified within 2 hours.

The customer must be notified of any CFSI finding. CFSI items must not be used or returned to the supply chain without customer authorisation.

CFSI is a growing risk in global supply chains. Nuclear customers take this extremely seriously. A single CFSI item entering a nuclear facility can have consequences for public safety. Every member of the team is responsible for being vigilant.

7. Lifetime Quality Records (LQR)

7.1 What Are Lifetime Quality Records?

Lifetime Quality Records are the complete set of documented evidence that the contracted products or services have been manufactured, inspected, and tested in full compliance with the specified requirements. They are called 'lifetime' records because they must be retained for the operating life of the nuclear facility, which can be 60 years or more.

The LQR package is submitted to the customer at contract close and becomes the customer's permanent evidence that the supplied items meet all requirements. Incomplete or poorly organised LQR packages are a common cause of delivery hold-ups and customer dissatisfaction.

7.2 LQR Compilation Principles

Records should be compiled concurrently during manufacture and inspection, not retrospectively at the end.

Every record must be legible, dated, signed by the responsible person, and cross-referenced to the relevant ITP activity.

Records must be traceable: from the specification requirement, through the inspection activity, to the specific item or batch.

Any gaps in the LQR must be identified and resolved before the final inspection hold point.

The LQR checklist in Quality Plan Section 12 must be completed and signed off before the LQR package is submitted.

7.3 LQR Retention

After submission to the customer, a copy of the complete LQR package must be retained by the company for a minimum of [10 years] or for the duration specified in the contract, whichever is longer. Retention location: [Define, e.g. quality management system, secure file server, physical archive].

8. Roles and Responsibilities Summary

| Role | Key Quality Planning Responsibilities |
| --- | --- |
| Managing Director | Approves the quality planning process; ensures adequate resource; reviews quality performance at management review |
| Quality Manager | Owns this process guide; prepares all quality plans and ITPs; manages NCR process; assembles LQR; maintains quality plan register |
| Contract Manager | Approves quality plans; chairs opening meetings; manages customer relationships; authorises change control |
| Lead Quality Inspector | Executes ITP inspection activities; signs off hold and witness points; raises NCRs; contributes to LQR compilation |
| All Manufacturing Personnel | Understand the quality plan requirements for their work; stop and raise an NCR if something is wrong; never proceed past a hold point without sign-off |
| Customer Quality Representative | Reviews and accepts quality plans and ITPs; attends hold and witness points; approves concessions and changes; accepts LQR package |

9. Process Review and Improvement

This process guide shall be reviewed annually by the Quality Manager, or following any significant quality event (such as a major NCR, customer complaint, or audit finding). Changes shall be approved by the Contract Manager, and the updated guide reissued under document control.

Lessons learned from completed contracts (captured in QHSE-QP-03 Sheet 5) shall be reviewed as part of each annual review and used to update this guide and the quality plan template where improvements are identified.

This document is the property of [Company Name] and is classified as Commercial in Confidence. It describes proprietary quality management processes and must not be shared externally without written authorisation from the Quality Manager.