## Material Register
INCOMING MATERIAL REGISTER
Log every incoming material at goods receipt. Verify certificate before releasing for use. Never use unverified material.
Mat. Ref | Date Received | Supplier | Delivery Note / PO Ref | Material Description | Grade / Spec. | Heat / Batch No. | Certificate Type | Certificate Ref. | CFSI Check Passed? | Inspector | Inspection Result | Storage Location | Released for Use? | Notes
MAT-001 | [Date] | [Supplier] | [PO Ref] | 316L Stainless Steel Bar 50mm dia | 316L / BS EN 10088-3 | [Heat No.] | EN 10204 Type 3.1 | [Cert Ref] | Yes | [Inspector] | Pass | Racking A / Bay 2 | Yes
MAT-002 | [Date] | [Supplier] | [PO Ref] | Carbon Steel Plate 25mm S355 | S355JR / BS EN 10025-2 | [Heat No.] | EN 10204 Type 3.1 | [Cert Ref] | Yes | [Inspector] | Pass | Plate Rack B | Yes
MAT-003 | [Date] | [Supplier] | [PO Ref] | Inconel 625 Bar 30mm dia | UNS N06625 / ASTM B446 | [Heat No.] | EN 10204 Type 3.2 | [Cert Ref] | Yes | [Inspector] | Pass | Quarantine then Racking C | Yes | Type 3.2 - customer witnessing required
MAT-004 | [Date] | [Supplier] | [PO Ref] | M20 High Tensile Bolts Grade 8.8 | BS EN ISO 4014 Gr 8.8 | [Batch No.] | EN 10204 Type 2.1 | [Cert Ref] | Yes | [Inspector] | Pass | Fastener Store Box 4 | Yes
MAT-005 | [Date] | [Supplier] | [PO Ref] | Welding Consumables ER316L MIG Wire | AWS A5.9 ER316L | [Lot No.] | Test Certificate | [Cert Ref] | Yes | [Inspector] | Pass | Consumable Store | Yes

## WIP Traveller Log
WIP TRAVELLER AND JOB CARD LOG
One row per job. Linked to material register. Status updated at each manufacturing stage.
Job Ref | Customer PO | Part No. / Drawing Ref | Rev | Qty | Material Ref (from Mat. Reg.) | Nuclear Classification | Current Stage | Traveller Status | Inspector Assigned | NCR Raised? | Target Completion | Notes
JOB-001 | [PO Ref] | [DRG-001] Pump Body | C | 2 | MAT-001, MAT-002 | QC2 | Final Inspection | Partially Complete | [Inspector] | No | [Date] | Awaiting final dimensional check
JOB-002 | [PO Ref] | [DRG-002] Valve Stem | A | 5 | MAT-001 | QC1 | NDT | Open | [Inspector] | No | [Date] | RT scheduled for [date]
JOB-003 | [PO Ref] | [DRG-003] Bracket Assembly | B | 10 | MAT-002 | QC3 | In Manufacture | Open | [Inspector] | Yes - NCR-001 | [Date] | NCR raised for dimensional deviation
JOB-004 | [PO Ref] | [DRG-004] Flange 150NB | D | 20 | MAT-002 | Non-Nuclear | Despatched | Closed | [Inspector] | No | [Date] | LQR submitted to customer

## Offcut Register
OFFCUT AND REMNANT MATERIAL REGISTER
All offcuts retained for reuse must be logged here. Unidentified offcuts are not permitted in the material store.
Offcut Ref | Date Cut | Original Material Ref | Material Grade / Spec. | Heat / Batch No. | Original Cert. Ref | Description / Dimensions | Job Cut From | Storage Location | Status | Used In Job | Notes
OC-001 | [Date] | MAT-001 | 316L SS Bar 50mm dia | [Heat No.] | [Cert Ref] | Offcut 320mm length | JOB-001 | Racking A Offcut Shelf | In Store |  | Yellow offcut tag attached
OC-002 | [Date] | MAT-002 | S355 Plate 25mm | [Heat No.] | [Cert Ref] | Plate offcut 450 x 300mm | JOB-003 | Plate Rack B Offcut Section | In Store |  | Yellow offcut tag attached
OC-003 | [Date] | MAT-002 | S355 Plate 25mm | [Heat No.] | [Cert Ref] | Plate offcut 200 x 150mm | JOB-003 | N/A | Scrapped | N/A | Too small for reuse - scrapped same day

## Quarantine Log
QUARANTINE LOG
All items quarantined (non-conforming, CFSI suspect, or unverified) must be logged here immediately. Quarantine must be physically enforced.
Quarantine Ref | Date Quarantined | Item Description | Quantity | Reason for Quarantine | Related NCR / CFSI Ref | Quarantined By | Quarantine Location | Customer Notified? | Investigation Outcome | Disposition | Date Cleared
QR-001 | [Date] | [Part description] | 3 | Dimensional deviation on bore diameter - outside drawing tolerance | NCR-001 | [Inspector] | Quarantine Area Bay 1 | No | Root cause: tooling wear. Rework feasible. | Rework | [Date]
QR-002 | [Date] | [Material description] | 1 heat | Material certificate does not match specification: grade stated is 304 not 316L as ordered | NCR-002 | [Inspector] | Quarantine Area Bay 1 | Yes - within 24 hours | Certificate error confirmed. Supplier issued replacement cert. | Accept - Return to Stock | [Date]
QR-003 | [Date] | [Component description] | 50 | CFSI suspect: packaging inconsistent with previous deliveries; price significantly below market rate | CFSI-001 | [Inspector] | CFSI Quarantine Store (locked) | Yes - customer notified immediately | Testing in progress with accredited lab | Under Investigation

## GR Inspection Record
GOODS RECEIPT INSPECTION RECORD
Complete one row per delivery. Verify certificate and carry out CFSI inspection before releasing any material.
GRI Ref | Date | Supplier | PO / DN Ref | Material / Item Description | Qty Received | Qty Accepted | Certificate Verified? | Certificate Meets Spec? | CFSI Inspection Passed? | Physical Condition | NCR / CFSI Ref (if raised) | Inspector Sign Off