## NCR Log
NON-CONFORMANCE REPORT (NCR) LOG
Raise a new NCR for every non-conformance. Notify the customer within 24 hours for QC1/QC2 items. Never proceed past a non-conformance without a disposition.
NCR Ref | Date Raised | Job / Order Ref | Part / Item Description | Drawing / Spec. Ref | Stage Detected | NCR Category | Description of Non-Conformance | Raised By | Disposition | Customer Notification Required? | Customer Notified Date | Root Cause Category | Corrective Action | Status | Date Closed
NCR-001 | [Date] | JOB-003 | Bracket Assembly [DRG-003] | DRG-003 Rev B | In-Process | Dimensional | Bore diameter measured at 25.32mm - drawing tolerance 25.00 +0.00/-0.05mm. Out of tolerance by 0.37mm. | [Inspector] | Rework | No | N/A | Process - Tooling Wear | Replace worn boring bar insert. Re-machine bore to tolerance. Re-inspect before proceeding. | Open
NCR-002 | [Date] | [PO Ref] | 316L Stainless Steel Bar | BS EN 10088-3 | Goods Receipt | Material / Traceability | Material certificate states Grade 304. Purchase order and specification require Grade 316L. Material does not meet specification. | [Inspector] | Return to Supplier | No | N/A | Supplier - Wrong Material Supplied | Contact supplier. Return all material from this delivery. Order replacement to correct specification. | Closed | [Date]
NCR-003 | [Date] | JOB-002 | Valve Stem [DRG-002] | DRG-002 Rev A | In-Process | Workmanship | Surface porosity identified during pre-weld visual inspection. Porosity present in HAZ of previous weld repair. Extent unknown. | [Inspector] | Under Review | Yes | [Date] | Process - Welding | Carry out RT to establish extent of porosity. Quality Manager to review findings and agree disposition with customer. | Customer Notified

## NCR Form
NON-CONFORMANCE REPORT (NCR)
Complete all sections. Quarantine the non-conforming item immediately. Notify the Quality Manager within 1 hour of raising.
SECTION 1: IDENTIFICATION
NCR Reference | NCR-
Date and Time Raised
Raised By (Name and Job Title)
Job / Order Reference
Part Number / Drawing Reference / Revision
Quantity Non-Conforming
Stage at Which NC Detected
Location of Non-Conforming Item
SECTION 2: DESCRIPTION OF NON-CONFORMANCE
Describe the non-conformance in detail: what was found, where, how it was identified, and what the requirement was.
SECTION 3: IMMEDIATE CONTAINMENT ACTION
Describe the immediate action taken to contain the non-conformance and prevent it spreading or being used inadvertently.
SECTION 4: CUSTOMER NOTIFICATION
Customer Notification Required? | Yes / No (circle one)
Reason if No
Date and Time Customer Notified
Customer Contact Notified (Name)
Customer Reference / Acknowledgement
SECTION 5: ROOT CAUSE ANALYSIS
Identify the root cause of the non-conformance. Use 5 Whys or fishbone analysis if appropriate. Do not accept "operator error" as a root cause - go deeper.
Root Cause Category
SECTION 6: DISPOSITION AND CORRECTIVE ACTION
Proposed Disposition | Rework / Repair / Use As Is / Scrap (delete as appropriate)
Technical Justification for Disposition
Corrective Action to Prevent Recurrence
Corrective Action Owner
Target Completion Date
SECTION 7: SIGN OFF
Raised By: Name / Signature / Date
Quality Manager: Name / Signature / Date
Customer Approval (if Repair or Use As Is): Name / Signature / Date / Reference
NCR Closed By: Name / Signature / Date

## RCA Tracker
ROOT CAUSE ANALYSIS AND CORRECTIVE ACTION TRACKER
Track all corrective actions to closure. Review trends monthly. Systemic issues must be addressed at management review.
NCR Ref | Date Raised | Root Cause Category | Root Cause Summary | Corrective Action | Action Owner | Target Date | Date Completed | Verification Method | Effective? | Status
NCR-001 | [Date] | Process - Tooling Wear | Boring bar insert life not tracked. Insert used beyond recommended life, causing dimensional deviation. | Implement tool life tracking on all CNC machines. Add insert change interval to machine setup sheet. Supervisor to verify insert condition at job start. | [Name] | [Date] | [Date] | Audit of tool life records; re-inspection of next 5 jobs from same machine | Yes - Closed | Closed
NCR-002 | [Date] | Supplier - Wrong Material Supplied | Supplier dispatched incorrect material grade due to picking error in their store. | Add material grade to purchase order in large, bold text. Add goods receipt check that grade on cert matches grade on PO. Issue supplier corrective action request. | [Name] | [Date] |  | Goods receipt check records; supplier response to SCAR | Pending Verification | In Progress

## Trend Analysis
NCR TREND ANALYSIS
Review NCR trends monthly. Recurring categories indicate systemic issues requiring management attention.
NCR Category | NCR Count by Month
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | TOTAL
Dimensional | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Material / Traceability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Workmanship | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CFSI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Supplier | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL
REVIEW GUIDANCE: Any category showing more than 2 NCRs in a single month, or more than 5 in a rolling quarter, indicates a systemic issue. This must be escalated to the Quality Manager and included in the next management review meeting. Trend data should be presented as part of the F4N Business Excellence evidence pack.

## Concession Log
CONCESSION AND DEVIATION LOG
Record all approved concessions (Use As Is or Repair dispositions). Customer written approval is mandatory before proceeding.
Concession Ref | Related NCR | Date Raised | Part / Item | Description of Non-Conformance | Technical Justification for Use As Is / Repair | Customer Approver | Customer Approval Ref | Date Approved | Engineering Sign Off | Status