## 🔴 Active Issues
SQDCP COUNTERMEASURES & ISSUES LOG
NucCol Fit For Nuclear Programme ¦ [Company Name] ¦ Active Issues — Updated Daily
This log captures all issues raised at the SQDCP board stand-up. Every RED result must generate an entry. Review open issues daily. Escalate overdue actions immediately.
# | Date Raised | Pillar | Issue Description | Root Cause (brief) | Countermeasure / Action | Owner | Due Date | Priority | Status | Date Closed
| DD/MM/YY | S/Q/D/C/P | Describe the issue clearly | Why did it happen? | What will be done to fix it? | Full name | DD/MM/YY | H / M / L | Open / Closed / Escalated | DD/MM/YY
1 | 01/01/[YY] | Safety | Near miss — forklift and pedestrian near collision in bay 3 | No defined pedestrian route in bay 3 | Install floor markings and bollards. Brief all staff in toolbox talk. | J. Smith | 08/01/[YY] | H | Open
2 | 01/01/[YY] | Quality | First pass yield dropped to 94% — below 98% target | Tool wear on CNC lathe not monitored — out of tolerance | Introduce tool life tracking. Implement pre-shift tool check SOP. | A. Khan | 15/01/[YY] | H | Open
3 | 01/01/[YY] | Delivery | Job 1042 at risk — 3 days behind schedule | Raw material delayed from supplier | Expedite material. Review supplier lead time in weekly review. | P. Yates | 10/01/[YY] | M | Open

## ✅ Closed Issues
SQDCP CLOSED ISSUES ARCHIVE
NucCol Fit For Nuclear Programme ¦ [Company Name] ¦ Closed Actions — For F4N Evidence
Move issues here once closed. Include before/after data wherever possible — closed countermeasures with measurable results are primary F4N evidence.
# | Date Raised | Pillar | Issue Description | Root Cause | Countermeasure / Action | Owner | Date Closed | Result / Improvement | Verified By | Lessons Learned
| DD/MM/YY | S/Q/D/C/P | Original issue | Root cause identified | Action taken | Owner | DD/MM/YY | Quantified result (before → after) | Manager name | What to do differently next time
1 | 15/12/[YY] | Quality | FPY dropped to 91% — 3 consecutive failures on part 447 | Tool wear — no inspection interval defined | Implemented 50-part tool life limit with mandatory inspection. SOP QP-22 updated. | A. Khan | 05/01/[YY] | FPY recovered to 98.5% within 2 weeks of countermeasure | Operations Manager | Preventive maintenance schedule to include tool life for all CNC machines

## ⚠️ Escalations
SQDCP ESCALATION REGISTER
NucCol Fit For Nuclear Programme ¦ Issues Escalated Beyond Team Level
Record any issue that cannot be resolved at team level. Escalation evidence is required for F4N Process Excellence assessment.
# | Date Raised | Pillar | Issue Description | Escalated To | Reason for Escalation | Date Escalated | Target Resolution | Outcome / Resolution | Status

## 📋 Instructions
SQDCP-04 Countermeasures & Issues Log — User Guide
HOW TO USE THIS LOG
1 | Raise an issue immediately | Any RED result at the daily stand-up must be entered in the Active Issues sheet before end of that working day. Don't wait until tomorrow.
2 | Complete all columns | Minimum required: Date, Pillar, Issue Description, Owner, Due Date, Priority, Status. Root cause and countermeasure should follow within 24 hours.
3 | Review open issues daily | The first agenda item of every stand-up is reviewing yesterday's open actions. Anything overdue must be escalated immediately.
4 | Close and archive | Once an action is verified complete, move the row to the Closed Issues sheet. Add the quantified result (before → after) for F4N evidence.
5 | Escalate when needed | If a team cannot resolve an issue within their authority or timescale, record it in the Escalation Register and notify the relevant manager.
6 | Priority coding | H = High (safety risk, customer impact, strategic KPI breach). M = Medium (performance below target, no immediate safety risk). L = Low (monitoring item).
F4N EVIDENCE NOTES
▶ | Closed issues with results | Countermeasures that show a before/after improvement are the strongest evidence for the Process Excellence and QHSE categories.
▶ | Issue volume is healthy | Having issues in this log is a sign of a healthy SQDCP culture, not a failing. Assessors are concerned by logs with no entries — it suggests the board isn't being used.
▶ | Retain historical logs | Keep at least 12 months of closed issues available for verification. Annual archive copies are ideal.
▶ | Link to KPI tracker | Reference the issue number from this log in the Notes column of SQDCP-03 (KPI Tracker) so assessors can trace KPI dips to countermeasures.