## Supply Chain Risk Register
SUPPLY CHAIN RISK REGISTER
Identify and manage risks across your supply chain. Review quarterly. Proactive risk management is a key F4N assessor focus.
Risk Ref | Supplier / Area | Risk Category | Risk Description | Potential Impact | Likelihood (1-5) | Severity (1-5) | Risk Score (L x S) | Risk RAG | Current Controls | Mitigation Actions | Action Owner | Review Date | Status
SCR-001 | [NDT Sub-contractor] | Single Source | Only one approved NDT sub-contractor with relevant PCN qualifications. Loss of this supplier would halt nuclear inspection activities. | Programme delay. Inability to meet ITP hold point commitments. Revenue at risk. | 3 | 5 | 15 | HIGH | Strong relationship maintained. Regular performance reviews. | Identify and qualify a second NDT supplier. Target completion: [Date]. | [Director] | [Date] | Open
SCR-002 | [Raw Material Supplier] | Financial / Insolvency | Key steel supplier is a single-site SME. Financial distress could cause sudden supply failure. | Material supply failure. Programme and cost impact. Emergency procurement at premium price. | 2 | 4 | 8 | MEDIUM | Monitor financial health via Companies House. Maintain 6-week buffer stock. | Add second approved steel supplier. Identify alternative source. | [Procurement] | [Date] | Under Mitigation
SCR-003 | ALL SUPPLIERS | CFSI | Counterfeit, Fraudulent, and Suspect Items entering the supply chain via legitimate-appearing suppliers. | Safety event. Plant contamination. Significant reputational and financial liability. | 2 | 5 | 10 | HIGH | CFSI procedure in place. Goods receipt inspection. Approved Supplier List controls. | Annual CFSI awareness toolbox talks. CFSI clause in all purchase orders. | [QM] | [Date] | Open
SCR-004 | [Specialist Coatings] | Lead Time / Capacity | Specialist coating supplier has 8-12 week lead time with no buffer capacity. Any disruption causes programme impact. | Delivery delays to nuclear customer. OTIF failure. Potential penalty clauses. | 3 | 3 | 9 | MEDIUM | Advance ordering where possible. Relationship managed at senior level. | Negotiate framework agreement with rolling call-off orders to improve supply security. | [Procurement] | [Date] | Open
SCR-005 | ALL SUPPLIERS | Geopolitical | Increasing geopolitical instability affecting raw material availability and freight costs. Particularly aluminium and specialist alloys. | Cost increase. Extended lead times. Potential shortage of critical materials. | 3 | 3 | 9 | MEDIUM | Monitor market. Diversify material sourcing where possible. | Review critical material stockholding. Identify alternative material sources. | [Procurement] | [Date] | Open
SCR-006 | [IT / Digital Supplier] | Cyber / Data | Supply chain management system (ERP / MRP) failure or cyber attack could disrupt procurement and scheduling. | Loss of purchasing, scheduling, and supply chain visibility. Business continuity risk. | 2 | 4 | 8 | MEDIUM | IT security controls in place. Business continuity plan references this risk. | Review ERP backup and recovery procedures. Confirm in BCM testing. | [IT/Operations] | [Date] | Open

## Risk Scoring Matrix
SUPPLY CHAIN RISK SCORING MATRIX
Use this matrix to score risks in the register. Likelihood x Severity = Score. HIGH = 10-25, MEDIUM = 5-9, LOW = 1-4.
SEVERITY
Likelihood / Severity | 1 - Negligible (Minor quality issue, easily corrected) | 2 - Minor (Rework required, limited cost impact) | 3 - Moderate (Contract disruption, significant cost) | 4 - Major (Programme failure, loss of approval) | 5 - Critical (Nuclear event, regulatory action, business failure)
5 - Almost Certain (Very likely within 12 months) | 25 HIGH | 20 HIGH | 15 HIGH | 10 HIGH | 5 MEDIUM
4 - Likely (Probable within 12 months) | 20 HIGH | 16 HIGH | 12 HIGH | 8 MEDIUM | 4 LOW
3 - Possible (Could occur in 1-3 years) | 15 HIGH | 12 HIGH | 9 MEDIUM | 6 MEDIUM | 3 LOW
2 - Unlikely (Possible but not expected) | 10 HIGH | 8 MEDIUM | 6 MEDIUM | 4 LOW | 2 LOW
1 - Rare (Unlikely in foreseeable future) | 5 MEDIUM | 4 LOW | 3 LOW | 2 LOW | 1 LOW
10-25: HIGH RISK: Escalate immediately. Director-level review required. Mitigation plan must be in place.
5-9: MEDIUM RISK: Actively manage. Include in quarterly review. Mitigation actions underway.
1-4: LOW RISK: Monitor. Annual review adequate. No immediate action required.

## Mitigation Tracker
RISK MITIGATION ACTION TRACKER
Track all mitigation actions from the risk register. Review monthly. Closed mitigations reduce risk scores.
Risk Ref | Mitigation Action | Owner | Start Date | Target Date | Progress Update | % Complete | Evidence of Completion | Risk Score After Mitigation | Status
SCR-001 | Identify and qualify a second NDT sub-contractor with relevant PCN qualifications for nuclear work. | [Director] | [Date] | [Date] | Market research complete. Two candidates identified. Qualification questionnaires issued. | 30% | Qualification questionnaires on file | Target: Reduce to MEDIUM (Score 6) | In Progress
SCR-002 | Add a second approved steel supplier. Complete qualification by [Date]. | [Procurement] | [Date] | [Date] | Supplier visited. ISO 9001 cert verified. EN 10204 capability confirmed. | 60% | Visit report and cert copies on file | Target: Reduce to LOW (Score 4) | In Progress
SCR-003 | Issue CFSI awareness clause in all new and renewed purchase orders. | [QM] | [Date] | [Date] | CFSI clause drafted and approved. Included in all new POs from [Date]. | 100% | PO template updated. QM sign-off on file | Score remains HIGH due to inherent risk. Controls strengthen defence. | Complete

## Review Schedule
SUPPLY CHAIN RISK REVIEW SCHEDULE
All HIGH risks reviewed monthly. MEDIUM reviewed quarterly. LOW reviewed annually. Review outcomes documented here.
Risk Ref | Risk Description | Risk Level | Review Frequency | Last Review Date | Next Review Due | Review Outcome | Actions Arising | Reviewed By
SCR-001 | Single NDT supplier | HIGH | Monthly | [Date] | [Date] | Risk level unchanged. Mitigation on track. | Chase qualification status of 2nd supplier candidate. | [Director]
SCR-002 | Key material supplier financial risk | MEDIUM | Quarterly | [Date] | [Date] | No deterioration. Buffer stock maintained at 6 weeks. | None at this review. | [Procurement Manager]
SCR-003 | CFSI across supply chain | HIGH | Monthly | [Date] | [Date] | CFSI clause now in all POs. GR inspection compliance rate 100%. | Schedule next CFSI awareness toolbox talk. | [QM]