## Instructions
NSS-03e ¦ NUCLEAR NON-CONFORMANCE REPORT AND TRACKER
PURPOSE | This workbook provides the nuclear-specific non-conformance reporting and tracking system required by ISO 19443 for ITNS work. It expands on generic NCR tools by including nuclear safety significance grading, formal disposition categories including concession management, and client notification requirements.
BOUNDARY WITH GENERIC NCR TOOLS | This system is for nuclear ITNS work only. Non-conformances on commercial, non-nuclear work should continue to use the company's standard NCR process. Where a non-conformance affects both nuclear and non-nuclear scope, the nuclear process takes precedence.
NUCLEAR SAFETY SIGNIFICANCE | Every nuclear NCR must be graded for nuclear safety significance: Grade 1 (potentially safety-significant, client notification required within 24 hours), Grade 2 (quality impact, no direct safety significance), Grade 3 (minor/administrative). Grade 1 NCRs must never be dispositioned without involving the client QA representative.
DISPOSITION OPTIONS | Rework: item brought back into conformance. Scrap: item destroyed and removed from the supply chain. Repair: non-standard repair carried out to approved procedure. Use As Is (Concession): item accepted in its non-conforming state with formal justification and client approval. Return to Supplier: item returned for supplier corrective action.
CONCESSION REQUIREMENT | Use As Is dispositions (concessions) require a formal technical justification documenting why the non-conformance does not affect the safety or functional performance of the item. Concessions must be approved by the Quality Lead and the client before the item is released. Concession records are lifetime quality records.
CLOSURE VERIFICATION | Every NCR must be closed with documented verification that the disposition has been completed satisfactorily. The verification must be signed off by the Quality Lead. Open NCRs must not be allowed to accumulate without active management.

## NCR Log
NSS-03e ¦ NUCLEAR NON-CONFORMANCE REPORT AND TRACKER
Company: |  |  | Log Owner: |  |  | Last Reviewed: |  |  | Version: 1.0
NCR Ref | Contract / PO Ref | Date Raised | Non-Conformance Description | Nuclear Safety Significance Grade | Client Notified? | Root Cause Category | Disposition | Concession Ref (if used) | Corrective Action | Owner | Target Date | Status | Date Closed
NCR-NUC-001 | PO-2025-047 | 2025-01-20 | Material certificate received does not match heat number stamped on bar stock. Certificate shows heat 4X2201, bar stamped 4X2199. Discrepancy cannot be resolved with supplier. | Grade 1 (Safety Significant) | Yes - Within 24hrs | Supplier Non-Conformance | Scrap |  | Material quarantined. New material ordered with enhanced verification. Supplier issued with formal corrective action request. | Quality Lead | 2025-02-03 | Closed | 2025-02-01
NCR-NUC-002 | PO-2025-047 | 2025-02-04 | Weld bead width on fillet weld #14 measures 4.8mm against minimum specified 5.0mm at three locations. Weld otherwise visually acceptable. | Grade 2 (Quality Impact) | Yes - Routine | Human Error | Use As Is (Concession required) | CON-001 | Formal concession raised. Stress calculation confirms 4.8mm bead still meets design loading requirements. Concession submitted to client for approval. Welder refresher training scheduled. | Quality Lead | 2025-02-14 | Awaiting Concession Approval
NCR-NUC-003 | PO-2025-031 | 2025-02-10 | Calibration sticker on vernier calliper found expired by 3 days. Calliper had been used for dimensional checks on items 22-27. | Grade 2 (Quality Impact) | Yes - Routine | Procedure Non-Compliance | Rework |  | Calliper removed from service immediately and sent for calibration. Items 22-27 re-inspected with calibrated equipment. All dimensions confirmed within tolerance. Calibration control procedure updated. | QC Inspector | 2025-02-17 | Closed | 2025-02-15

## Concession Register
NSS-03e ¦ CONCESSION REGISTER
Concession Ref | Linked NCR | Date Raised | Non-Conformance Description | Technical Justification (Summary) | Scope of Concession (item/batch) | Client Approval Ref | Date Approved | Status

## Dashboard
NSS-03e ¦ NCR DASHBOARD
Metric | Count
Total NCRs Raised
Grade 1 (Safety Significant) NCRs
Grade 2 (Quality Impact) NCRs
Grade 3 (Minor) NCRs
Open NCRs
NCRs Awaiting Concession Approval
Closed NCRs
Use As Is Dispositions (Concessions)
CFSI-Related NCRs
NCRs from Supplier Non-Conformance