## Instructions
NUCLEAR PROCUREMENT REQUIREMENTS FLOW-DOWN TRACKER
NSS-06-EX-02 ¦ NucCol ¦ Nuclear Sector Specific - Supply Chain Readiness
PURPOSE | This tracker records the nuclear requirements placed on your organisation by the buyer and tracks how each requirement has been flowed down to relevant subcontractors. It provides documented evidence that flow-down has been completed and verified.
HOW TO USE | Complete the Contract Register sheet for each nuclear contract. For each contract, populate the Requirements Register with all nuclear-specific requirements. Use the Flow-Down Status sheet to record how each requirement has been communicated to each subcontractor.
REQUIREMENT SOURCE | Requirements may originate from the contract, the buyer's supply chain management procedure, the applicable design code, the nuclear safety case, ONR requirements, or industry standards. Record the source for each requirement to enable traceability.
VERIFICATION | Each flow-down entry must record how the requirement was communicated (purchase order clause, specification section, etc.) and how compliance was verified (quality plan review, ITP check, audit, etc.). Unverified flow-down is incomplete flow-down.
RAG STATUS | Red = requirement not yet flowed down. Amber = communicated but not yet verified. Green = communicated and verified with objective evidence.

## Contract Register
CONTRACT REGISTER
Contract Ref | Buyer / Customer | Project Name | Contract Date | Nuclear Safety Class | Scope Description | Contract Manager | Quality Manager | Subcontractors Used | Contract Value (approx) | Completion Date | Archive Location
CON-001 | [Buyer Name] | [Project Name] | 2025-01-15 | NSC2 | Manufacture and supply of pressure vessel assembly for secondary cooling circuit | [Contract Manager] | [Quality Manager] | 3 subcontractors | Commercially Sensitive | 2026-06-30 | DMS > Projects > CON-001

## Requirements Register
NUCLEAR REQUIREMENTS REGISTER
Req Ref | Contract Ref | Requirement Category | Requirement Description | Source Document / Clause | Safety Significance | Applicable to Subcontractors? | Flow-Down Required | Date Identified | Identified By
REQ-001 | CON-001 | Quality Plan | Supplier to prepare and submit Quality Plan for purchaser approval before manufacture commences | Contract Clause 4.2 / ISO 19443:2018 Clause 8.4 | High | Yes | Yes | 2025-01-20 | [Name]
REQ-002 | CON-001 | CFSI Control | All materials to be sourced from OEM or OEM-authorised distributor. Full material traceability documentation required to mill certificate level | Contract Clause 7.1 / TAG 77 Section 5.2.8 | High | Yes | Yes | 2025-01-20 | [Name]
REQ-003 | CON-001 | ITP / Hold Points | Supplier to prepare ITP. Purchaser hold point at pressure test and final dimensional inspection. 5 working days notice required | Contract Clause 4.3 / Customer SCM Procedure SCM-QA-004 | High | Yes | Yes | 2025-01-20 | [Name]
REQ-004 | CON-001 | Records | Full quality records package to be submitted with delivery: mill certs, weld records, NDE reports, pressure test cert, CoC | Contract Schedule B / ISO 19443 Clause 7.5 | High | Yes | Yes | 2025-01-20 | [Name]
REQ-005 | CON-001 | SQEP | Welders to hold valid CSWIP 3.1 certification. NDT personnel to hold PCN Level 2 minimum. Certification records to be submitted for purchaser review before work commences | Contract Clause 5.1 / NS-TAST-GD-027 | Medium | Yes | Yes | 2025-01-20 | [Name]
REQ-006 | CON-001 | Change Control | No changes to materials, processes, sub-tier suppliers or design without prior written approval from purchaser | Contract Clause 9.1 / TAG 77 Section 5.2.6 | High | Yes | Yes | 2025-01-20 | [Name]
REQ-007 | CON-001 | Right of Access | Purchaser reserves right to conduct inspection and audit at supplier premises and any sub-tier supplier used, with 48 hours notice | Contract Clause 11.1 / TAG 77 Section 5.2.7 | Medium | Yes | Yes | 2025-01-20 | [Name]

## Flow-Down Status
REQUIREMENTS FLOW-DOWN STATUS TRACKER
Flow-Down Ref | Contract Ref | Req Ref | Subcontractor Name | Requirement Summary | Method of Communication | PO Clause / Reference | Date Communicated | Verification Method | Date Verified | Verified By | Flow-Down Status
FD-001-001 | CON-001 | REQ-001 | [Subcontractor A] | Quality Plan required, purchaser approval before manufacture | Purchase Order condition | PO-CON001-SUB-A, Clause 4.2 | 2025-02-03 | Quality Plan received and reviewed against requirements | 2025-02-14 | [Name] | VERIFIED
FD-001-002 | CON-001 | REQ-002 | [Subcontractor A] | CFSI: OEM sourcing, full traceability to mill certificate | Purchase Order condition + CFSI Schedule | PO-CON001-SUB-A, Clause 7.1 + Schedule C | 2025-02-03 | Material certs reviewed at goods receipt | 2025-03-15 | [Name] | VERIFIED
FD-001-003 | CON-001 | REQ-003 | [Subcontractor A] | ITP required; hold points at pressure test and final inspection | Purchase Order condition | PO-CON001-SUB-A, Clause 4.3 | 2025-02-03 | ITP received and approved. Hold points confirmed. | 2025-02-18 | [Name] | VERIFIED
FD-001-004 | CON-001 | REQ-001 | [Subcontractor B] | Quality Plan required, purchaser approval before manufacture | Purchase Order condition | PO-CON001-SUB-B, Clause 4.2 | 2025-02-05 | Quality Plan submitted. Review in progress. |  |  | COMMUNICATED
FD-001-005 | CON-001 | REQ-005 | [Subcontractor C] | Welders: CSWIP 3.1 minimum. NDT: PCN Level 2 minimum | Purchase Order condition | PO-CON001-SUB-C, Clause 5.1 |  |  |  |  | NOT STARTED

## Summary
FLOW-DOWN COMPLIANCE SUMMARY
Total Requirements Identified
Total Flow-Down Records
Verified
Communicated (Pending Verification)
Not Started
% Complete (Verified)