## Instructions
SUPPLIER PERFORMANCE AND SURVEILLANCE DASHBOARD
NSS-06-EX-03 ¦ NucCol ¦ Nuclear Sector Specific - Supply Chain Readiness
PURPOSE | This workbook tracks the ongoing performance of approved nuclear suppliers and records all surveillance activities. It provides a structured basis for supplier performance reviews and supports the evidence requirement for ongoing oversight under TAG 77 and ISO 19443.
PERFORMANCE DATA | Record monthly performance data in the Performance Data sheet for each supplier. Scoring is on a 1-5 scale for each KPI. The Dashboard sheet provides a consolidated view and automatically calculates overall ratings.
SURVEILLANCE LOG | Record all surveillance visits, inspection attendance and document reviews in the Surveillance Log. This provides a complete audit trail of purchaser oversight activity.
NCR TRACKER | Log all Non-Conformance Reports raised against supplier deliveries. Track corrective action progress and verify close-out with objective evidence.
PERFORMANCE RATINGS | 5 = Excellent: consistently exceeds requirements. 4 = Good: meets requirements with minor issues. 3 = Satisfactory: generally meets requirements. 2 = Marginal: recurring minor issues or isolated major issue. 1 = Poor: significant failures requiring immediate action.

## Performance Data
SUPPLIER PERFORMANCE DATA
Score each KPI 1-5 (5=Excellent, 1=Poor). Overall score and RAG calculated automatically.
ASL Ref | Supplier Name | Period (Month/Year) | On-Time Delivery (1-5) | Quality: NCR Rate (1-5) | Quality: Documentation (1-5) | Responsiveness (1-5) | Audit Cooperation (1-5) | CFSI Compliance (1-5) | Safety Culture Indicators (1-5) | Overall Score | RAG Status | Review Date | Reviewer
ASL-001 | [Supplier A] | Jan 2025 | 4 | 4 | 5 | 4 | 5 | 5 | 4 |  |  | [Date] | [Reviewer]
ASL-001 | [Supplier A] | Feb 2025 | 4 | 3 | 4 | 4 | 5 | 5 | 4 |  |  | [Date] | [Reviewer]
ASL-001 | [Supplier A] | Mar 2025 | 5 | 4 | 5 | 5 | 5 | 5 | 5 |  |  | [Date] | [Reviewer]
ASL-002 | [Supplier B] | Jan 2025 | 3 | 3 | 3 | 3 | 4 | 4 | 3 |  |  | [Date] | [Reviewer]
ASL-002 | [Supplier B] | Feb 2025 | 2 | 3 | 3 | 3 | 4 | 4 | 3 |  |  | [Date] | [Reviewer]
ASL-003 | [Supplier C] | Jan 2025 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | [Date] | [Reviewer]
ASL-003 | [Supplier C] | Feb 2025 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | [Date] | [Reviewer]

## Surveillance Log
SUPPLIER SURVEILLANCE AND INSPECTION LOG
Surveillance Ref | ASL Ref | Supplier Name | Activity Type | Contract Ref | Date of Activity | Inspector Name | ITP Ref / Activity | Outcome | Non-Conformances Identified | Follow-Up Required | Follow-Up Complete
SUR-001 | ASL-001 | [Supplier A] | Hold Point Inspection | CON-001 | 2025-03-14 | [Inspector] | ITP Rev 2, Step 14: Pressure Test | PASS - Released for further processing | 0 | No | N/A
SUR-002 | ASL-001 | [Supplier A] | Witness Point Inspection | CON-001 | 2025-02-28 | [Inspector] | ITP Rev 2, Step 10: Final dimensional inspection | PASS with observation - minor burr on one flange face, supplier to clean before assembly | 1 | Yes | Open - target 14/03/2025
SUR-003 | ASL-002 | [Supplier B] | Surveillance Visit | CON-002 | 2025-01-22 | [Inspector] | General in-process surveillance: welding and fabrication | SATISFACTORY - good housekeeping. Welding procedures current. 1 minor observation on PPE compliance | 1 | Yes | Closed 29/01/2025
SUR-004 | ASL-003 | [Supplier C] | Goods Receipt Inspection | CON-001 | 2025-03-20 | [Inspector] | GRI-CON001-003: Electrical cable assemblies | ACCEPTED - all documents complete and correct. PMI test satisfactory. | 0 | No | N/A

## NCR Tracker
NON-CONFORMANCE REPORT TRACKER
NCR Ref | ASL Ref | Supplier Name | Contract Ref | NCR Date | Description of Non-Conformance | Classification | Disposition | Disposition Approved By | CAP Submitted Date | CAP Due Date | Closed Date | Status
NCR-001 | ASL-001 | [Supplier A] | CON-001 | 2025-02-28 | Burr on flange face - item does not meet finish specification Clause 6.2.4 | Minor | Rework: supplier to remove burr and resubmit for inspection | [Name] | 2025-03-04 | 2025-03-14 |  | OPEN
NCR-002 | ASL-002 | [Supplier B] | CON-002 | 2025-01-18 | Weld procedure revision W-201 Rev 3 used. Only W-201 Rev 2 was approved on ITP | Major | Rework not required: engineering assessment confirms Rev 3 changes do not affect weld quality. Procedure re-approval raised | [Name] | 2025-01-24 | 2025-02-07 | 2025-02-06 | CLOSED

## Dashboard
SUPPLIER PERFORMANCE DASHBOARD
Summary view drawing from Performance Data, Surveillance Log and NCR Tracker.
Total Surveillance Activities |  | Total NCRs Raised |  | Open NCRs |  | Major NCRs |  | Suppliers at RED Performance
SUPPLIER PERFORMANCE SUMMARY (LATEST MONTH)
ASL Ref | Supplier Name | Delivery | Quality (NCR) | Quality (Docs) | Responsiveness | Audit Coop | CFSI | Safety Culture | Overall
1 | [Supplier A]
1 | [Supplier B]
1 | [Supplier C]