FLOW-DOWN OF NUCLEAR REQUIREMENTS

Managing Subcontractor Compliance in the Nuclear Supply Chain

A working guide to ensuring nuclear requirements are effectively communicated and controlled throughout all tiers of the supply chain

[Company Name]  |  NSS-06-TG-03

Document Control

| Version | Date | Author | Description |
| --- | --- | --- | --- |
| 1.0 | 29/06/2026 | [Company Name] | Initial issue |

1.  Introduction

In nuclear projects, responsibility for quality and safety does not stop at your organisation's boundary. If you use subcontractors to perform work that contributes to a nuclear delivery, you are responsible for ensuring that they understand and apply the same nuclear requirements that your customer has placed on you.

This is the principle of requirements flow-down: the systematic communication and verification of nuclear requirements from the top-tier buyer, through each tier of the supply chain, to every organisation that performs work or supplies materials that contribute to the final nuclear product or service.

Responsibility for nuclear safety in the supply chain is not diluted by subcontracting. If you subcontract a nuclear activity, you remain accountable for the quality and safety of the work delivered.

This guide explains what effective flow-down looks like in practice, how to structure purchase orders and subcontracts to communicate requirements, how to verify that subcontractors are applying them, and how to manage changes and deviations.

1.1  Why Flow-Down Fails

In practice, flow-down breaks down for predictable reasons:

•  Nuclear requirements are stated in high-level contracts but not translated into the subcontractor's purchase order.

•  Subcontractors are assumed to know nuclear requirements because they hold ISO 9001 or have worked in the sector before.

•  Requirements are communicated verbally rather than in writing.

•  Purchase orders reference general quality requirements but not the specific nuclear grade, applicable codes or documentation expectations.

•  Changes to requirements made during the project are not communicated to subcontractors in time.

These failures can result in non-conformances discovered late in the manufacturing process, delays to inspection and testing, and, in the worst cases, items delivered to site that do not meet the safety case requirements.

2.  What Must Be Flowed Down

2.1  Mandatory Flow-Down Elements

For any subcontract that involves nuclear-grade work, the following elements must be communicated in writing, either in the purchase order or an attached technical specification:

| Element | Why It Must Be Communicated | How It Is Typically Communicated |
| --- | --- | --- |
| Nuclear safety classification | The subcontractor must know the grade of the item to apply the correct quality programme. | Specification clause or purchase order condition |
| Applicable codes and standards | The subcontractor must know which technical standards govern their work. | Purchase order or appended specification |
| Quality plan requirement | Where a quality plan is required, the subcontractor must know this before work starts. | Purchase order condition with approval route defined |
| ITP and hold / witness points | The subcontractor must submit an ITP and not pass hold points without your sign-off or waiver. | ITP requirement stated in PO; hold points defined |
| CFSI requirements | The subcontractor must source from approved channels and maintain material traceability. | CFSI clause in purchase order terms and conditions |
| Right of access | You must retain the right to inspect and audit the subcontractor's premises and any sub-tier suppliers. | Standard purchase order condition |
| Documentation requirements | The subcontractor must know exactly what records to deliver with the item. | Appended documentation register or PO schedule |
| Non-conformance reporting | The subcontractor must notify you of any non-conformance before proceeding. | Purchase order condition; NCR procedure reference |
| Change control | Any proposed changes to materials, processes or design must be notified and approved before implementation. | Purchase order condition; reference to change control procedure |
| Retention period for records | The subcontractor must retain records for the required period. | Purchase order condition — typically "life of plant plus 30 years" for safety-significant items |

2.2  Proportionality

Not all subcontracts require the same level of flow-down detail. The depth and formality of flow-down should be proportionate to:

•  The nuclear safety classification of the item or service.

•  The complexity of the work being subcontracted.

•  The subcontractor's experience and track record in nuclear work.

•  The level of risk associated with the procurement (including CFSI risk).

A subcontract for a safety-class pressure vessel requires a very different flow-down regime from a subcontract for general consumables used in non-nuclear activities on the same site.

3.  Structuring the Purchase Order

3.1  Nuclear Purchase Order Structure

A nuclear purchase order is more than a commercial document. It is the mechanism by which requirements are formally communicated and contractually binding. A well-structured nuclear purchase order should contain the following parts:

Part 1: Commercial Terms

Standard commercial terms including price, delivery, payment terms and warranty provisions. Any nuclear-specific commercial conditions — such as the right to suspend work if a hold point is not released — should be included here.

Part 2: Technical Specification

The technical requirements including item description, dimensions, materials, performance requirements, applicable codes and standards (with issue numbers), and nuclear safety classification.

Part 3: Quality Requirements

The quality programme requirements including the grade of quality plan required, ITP requirements, hold and witness points, SQEP requirements, and any special process qualifications needed.

Part 4: Documentation Requirements

A complete list of the documents and records that must be delivered with the item. This should be specific — do not use phrases like "full documentation pack" without defining what this means.

Part 5: CFSI and Traceability Requirements

Requirements for sourcing from approved channels, material traceability documentation, and enhanced inspection and testing for CFSI-risk items.

3.2  Common Mistakes in Nuclear Purchase Orders

Avoid the following common mistakes when drafting nuclear purchase orders:

•  Referencing standards without specifying the issue number or date, allowing the subcontractor to apply the wrong version.

•  Stating that "nuclear quality requirements apply" without defining what this means for the specific item or service.

•  Failing to include the right of access clause, which may prevent you from auditing sub-tier suppliers.

•  Attaching a generic quality requirements schedule that is not tailored to the specific item or service being procured.

•  Not defining who the responsible person is for approving the quality plan and ITP.

4.  Verifying Flow-Down Effectiveness

4.1  Quality Plan Review

Where a quality plan is required, it is the primary document through which the subcontractor demonstrates their understanding of the requirements. When reviewing a subcontractor's quality plan, check the following:

•  Has the subcontractor correctly identified the nuclear safety classification of the item?

•  Have all applicable codes and standards been referenced?

•  Have all the hold and witness points specified in the purchase order been included in the ITP?

•  Has the subcontractor included the CFSI controls required by the purchase order?

•  Has the documentation schedule been correctly reproduced and any additional documents identified?

•  Are the personnel identified as responsible for key activities confirmed as SQEP for those activities?

If the quality plan does not adequately reflect the purchase order requirements, it must be returned to the subcontractor for revision before work starts.

4.2  ITP Review and Hold Point Management

The Inspection and Test Plan (ITP) defines every inspection and test activity to be performed during manufacture or service delivery. Each hold and witness point you have specified must be:

•  Clearly identified in the ITP with your organisation's role (e.g. "customer review required" or "hold — customer sign-off required before proceed").

•  Communicated to the subcontractor in advance so they can plan inspection notification timescales into their programme.

•  Formally released in writing (typically by signing the ITP record) before the subcontractor proceeds.

Witness points are similar to hold points but allow the subcontractor to proceed if you give notice that you will not attend. Hold points are absolute stops — the subcontractor cannot proceed without your written release regardless of programme pressure.

4.3  Records Review

At delivery, carry out a systematic review of the documentation package submitted by the subcontractor against the documentation requirements in the purchase order. Do not accept delivery until the documentation package is complete and verified.

Incomplete or incorrect documentation is a non-conformance and should be treated as such. Do not accept items into your facility or onto site with outstanding documentation — the documentation is as much a part of the nuclear deliverable as the physical item.

5.  Managing Changes and Deviations

5.1  Change Control in Nuclear Subcontracts

Nuclear requirements are based on safety cases and design specifications that are fixed at the point of procurement. Any change to the agreed scope of work, materials, processes or sub-tier suppliers must therefore be controlled.

The change control requirement must be stated in the purchase order. The subcontractor must be required to notify you — and obtain written approval — before making any change to:

•  Materials (including any substitution of specified materials).

•  Manufacturing processes (including changes to welding procedures, heat treatment, or special processes).

•  Sub-tier suppliers used in the manufacture of the item.

•  Personnel performing safety-significant activities.

•  The design of the item, where the subcontractor has design responsibility.

5.2  Non-Conformance Management

Despite the best controls, non-conformances will occur. What matters is that they are identified, reported, controlled and dispositioned correctly. A non-conformance is any departure from a specified requirement.

The non-conformance management process for nuclear subcontracts should follow these steps:

•  The non-conformance is recorded on a formal NCR with a unique reference number.

•  The item or area affected is quarantined to prevent inadvertent use or further processing.

•  The NCR is submitted to you for review and disposition decision.

•  You determine the disposition: repair, rework, use-as-is (with engineering justification), or reject.

•  If the disposition affects the design intent or safety case, it must be referred to the design authority or licensee.

•  The agreed disposition is implemented and the NCR record is updated to reflect the close-out evidence.

Use-as-is dispositions require particular care. They must be supported by a documented engineering justification demonstrating that the non-conforming item still meets its functional and safety requirements.

6.  Sub-Tier Supplier Oversight

6.1  Your Responsibility for Sub-Tier Suppliers

If your subcontractor uses their own sub-tier suppliers to perform part of the work, your responsibility for the nuclear requirements does not end at the first tier. Your purchase order must therefore require your subcontractor to:

•  Apply the same flow-down requirements to their own suppliers as you have applied to them.

•  Maintain an approved supplier list (ASL) for nuclear work that you have the right to review.

•  Obtain your approval before using a sub-tier supplier for safety-significant activities.

•  Grant you the right of access to any sub-tier supplier's premises.

6.2  Assessing Sub-Tier Compliance

Assessing whether sub-tier flow-down is actually effective is challenging, particularly in complex multi-tier supply chains. Practical approaches include:

•  Requiring the subcontractor to submit their sub-tier purchase orders for your review on request.

•  Including sub-tier supplier oversight as part of your audit of the subcontractor.

•  Conducting direct surveillance visits at sub-tier supplier premises where the risk level warrants it.

•  Requiring the subcontractor to provide sub-tier quality plan and ITP records as part of the final documentation package.

The complexity of a nuclear supply chain does not reduce the requirement for compliance at every tier. Your nuclear customer will hold you accountable for the performance of your entire supply chain.

7.  Quick Reference: Flow-Down Checklist

Use this checklist for every nuclear subcontract to verify that flow-down is complete before placing the purchase order.

| Requirement | Included in PO? | Reference |
| --- | --- | --- |
| Nuclear safety classification stated | ☐ Yes ☐ No |  |
| Applicable codes and standards listed with issue numbers | ☐ Yes ☐ No |  |
| Quality plan requirement stated (with approval route) | ☐ Yes ☐ No |  |
| ITP requirement stated (hold and witness points defined) | ☐ Yes ☐ No |  |
| CFSI clause included | ☐ Yes ☐ No |  |
| Material traceability requirement stated | ☐ Yes ☐ No |  |
| Right of access clause included | ☐ Yes ☐ No |  |
| Non-conformance reporting requirement stated | ☐ Yes ☐ No |  |
| Change control requirement stated | ☐ Yes ☐ No |  |
| Documentation and records schedule appended | ☐ Yes ☐ No |  |
| Records retention period stated | ☐ Yes ☐ No |  |
| Sub-tier flow-down requirement stated | ☐ Yes ☐ No |  |